## 2 · RFC PROGRESS
PS5 COMPLETION PLATFORM ¦ 2 · RFC PROGRESS
SUB SYSTEM | PRIO | RFC BHM | RFC EIT | BASE | RECOV | SIGNED | MILESTONE | TOT% | B |  |  | E |  |  | H |  |  | I |  |  | M |  |  | P |  |  | S |  |  | T |  |  | ITRs | CL | BAL | ITR% | CPP | EIT | EACP | REMARK E | REMARK C | REMARK 1 | WALKDOWN | ● | MY NOTES
[9 empty] | T | CL | % | T | CL | % | T | CL | % | T | CL | % | T | CL | % | T | CL | % | T | CL | % | T | CL | %
PS5-01-01 - Fire Water Jockey Pump A/B | 1.1 | Yes | E,I,M,P | CPP 1 |  | - | PS5 - Milestone C | 49% | 0 | 24 | 0 | 60 | 14 | 30 | 0 | 0 | 0 | - | [14 empty] | 128 | 44 | 84 | 34% | 0 | 0 | 0
PS5-01-02 - Fire Water Pump A | 1.1 | Yes | E,I,M,P | 2026-09-07 00:00:00 |  | - | PS5 - Milestone C | 59% | 0 | 13 | 0 | 40 | 10 | 51 | 0 | 0 | 0 | - | [14 empty] | 114 | 50 | 64 | 44% | 0 | 0 | 0
PS5-01-03 - Fire Water Pump B | 1.1 | Yes | E,I,M,P | 2026-09-08 00:00:00 |  | - | PS5 - Milestone C | 58% | 0 | 13 | 0 | 36 | 11 | 46 | 0 | 0 | 0 | - | [14 empty] | 106 | 45 | 61 | 42% | 0 | 0 | 0
PS5-01-04 - Fire Water Pump Mini Flow Recycle | 1.1 | Yes | P | 2026-09-08 00:00:00 |  | - | PS5 - Milestone C | 50% | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | - | [14 empty] | 10 | 4 | 6 | 40% | 0 | 0 | 0
PS5-01-05 - Foam Skid | 2 | Yes | E,I,M,P | 2026-09-16 00:00:00 |  | - | PS5 - Milestone F | 50% | 0 | 15 | 0 | 24 | 9 | 12 | 0 | 0 | 0 | - | [14 empty] | 60 | 14 | 46 | 23% | 0 | 0 | 0
PS5-01-06 - Foam Concentrate Distribution | 2 | Yes | P | 2026-09-16 00:00:00 |  | - | PS5 - Milestone F | 62% | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | - | [14 empty] | 10 | 5 | 5 | 50% | 0 | 0 | 0
PS5-01-07 - Fire Water Ring Main & Distribution | 2 | Yes | I,P,S | 2026-10-08 00:00:00 |  | - | PS5 - Milestone C | 51% | 0 | 0 | 0 | 29 | 4 | 89 | 29 | 0 | 0 | - | [14 empty] | 151 | 70 | 81 | 46% | 0 | 0 | 0
PS5-01-08 - PS5 Deluge Valve Skid (PS5-01-UK-6100) | 2 | Yes | E,I,M,P,S | 2026-10-09 00:00:00 |  | - | PS5 - Milestone F | 52% | 0 | 6 | 0 | 21 | 4 | 36 | 8 | 0 | 0 | - | [14 empty] | 75 | 31 | 44 | 41% | 0 | 0 | 0
PS5-01-09 - Inergen for EITS Building | 1 | Yes | P | Complete |  | 2026-08-08 00:00:00 | PS5 - Milestone A | 100% | 0 | 2 | 0 | 207 | 2 | 7 | 0 | 0 | 0 | - | [14 empty] | 218 | 217 | 1 | 100% | 0 | 0 | 0
PS5-01-10 - Water Mist Package | 1.1 | Yes | E,I,M,P | 2026-09-12 00:00:00 |  | - | PS5 - Milestone E | 46% | 0 | 8 | 0 | 89 | 5 | 49 | 0 | 0 | 0 | - | [14 empty] | 151 | 52 | 99 | 34% | 0 | 0 | 0
PS5-01-11 - Inergen for Power Gen Building | 1.1 | Yes | E,I,M,P | 2026-09-01 00:00:00 |  | - | PS5 - Milestone E | 4% | 0 | 11 | 0 | 99 | 3 | 3 | 0 | 0 | 0 | - | [14 empty] | 116 | 5 | 111 | 4% | 0 | 0 | 14
PS5-02-01 - Miscellaneous Safety equipment | 3 | Yes | E,M,S | 2026-10-25 00:00:00 |  | - | PS5 - Milestone H | 8% | 0 | 7 | 0 | 2 | 5 | 0 | 61 | 0 | 0 | - | [14 empty] | 75 | 8 | 67 | 11% | 0 | 0 | 0
PS5-02-02 - Portable Fire Fighting Equipments | 3 | Yes | M,S | 2026-10-03 00:00:00 |  | - | PS5 - Milestone H | 1% | 0 | 0 | 0 | 0 | 3 | 0 | 82 | 0 | 0 | - | [14 empty] | 85 | 7 | 78 | 8% | 0 | 0 | 0
PS5-03-01 - FZ-01 - Process Area | 2 | Yes | E,I | N/A |  | - | PS5 - Milestone H | 26% | 0 | 26 | 0 | 197 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 223 | 40 | 183 | 18% | 0 | 0 | 0
PS5-03-03 - FZ-03 - Buildings Area | 5 | Yes | I | N/A |  | - | PS5 - Milestone H | 6% | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 26 | 1 | 25 | 4% | 0 | 0 | 0
PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | 1.1 | Yes | E,I | N/A |  | - | PS5 - Milestone F | 38% | 0 | 5 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 53 | 13 | 40 | 25% | 0 | 0 | 0
PS5-03-06 - FZ-06 - Transformer Area | 2 | Yes | I | N/A |  | - | PS5 - Milestone E | 24% | 0 | 0 | 0 | 86 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 86 | 15 | 71 | 17% | 0 | 0 | 0
PS5-03-07 - FZ-07 - Pretreatment Area | 2 | Yes | I | N/A |  | - | PS5 - Milestone E | 4% | 0 | 0 | 0 | 34 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 34 | 1 | 33 | 3% | 0 | 0 | 0
PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | 2 | Yes | I | N/A |  | - | PS5 - Milestone E | 19% | 0 | 0 | 0 | 73 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 73 | 9 | 64 | 12% | 0 | 0 | 0
PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | 1 | Yes | I | N/A | HOLD/meterial issue | - | PS5 - Milestone E | 50% | 0 | 0 | 0 | 78 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 78 | 42 | 36 | 54% | 0 | 0 | 0 | Due to gland plate issue of SEA-0001 we cannot terminate the cablesof F&G Instruments.
PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | 1.1 | Yes | I | N/A |  | - | PS5 - Milestone E | 16% | 0 | 0 | 0 | 81 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 81 | 10 | 71 | 12% | 0 | 0 | 0
PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | 2 | Yes | I | N/A |  | - | PS5 - Milestone E | 3% | 0 | 0 | 0 | 81 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 81 | 2 | 79 | 2% | 0 | 0 | 0
PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | 2 | Yes | I | N/A |  | - | PS5 - Milestone E | 6% | 0 | 0 | 0 | 46 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 46 | 2 | 44 | 4% | 0 | 0 | 0
PS5-03-13 - FZ-13 - Power Generation Building - Instrument Air Room | 1.1 | Yes | I | N/A |  | - | PS5 - Milestone E | 0% | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 18 | 0 | 18 | 0% | 0 | 0 | 0
PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | 1 | Yes | E,I,M,T | complete | HOLD/meterial issue | - | PS5 - Milestone E | 25% | 0 | 10 | 0 | 90 | 2 | 0 | 0 | 3 | 1 | 33% | [14 empty] | 105 | 23 | 82 | 22% | 0 | 0 | 24 | cannot start termination due to unavailabiity of gland plate sketch. 3 manual call point not arrived yet PS5-03-RMAC-1409~1411 8 Smake detectors not arrived yet PS5-03-RDOS-1401~1408 11 cables for RMAC/RDOS not arrived yet 1P X 1.0 OS FR 275m
PS5-03-15 - FZ-15 - Power Generation Building - Generator Room 1 | 1 | Yes | I | N/A | HOLD/meterial issue | - | PS5 - Milestone E | 0% | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 11 | 0 | 11 | 0% | 0 | 0 | 6 | PS5-03-RDOS-1501/1502/1503 not arrived
PS5-03-16 - FZ-16 - Power Generation Building - Generator Room 2 | 1.1 | Yes | I | N/A |  | - | PS5 - Milestone E | 0% | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 11 | 0 | 11 | 0% | 0 | 0 | 6 | PS5-03-RDOS-1601/1602/1603 not arrived yet
PS5-03-17 - FZ-17 - Power Generation Building - Generator Room 3 | 2 | Yes | I | N/A |  | - | PS5 - Milestone E | 0% | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 11 | 0 | 11 | 0% | 0 | 0 | 0
PS5-03-18 - FZ-18 - Power Generation Building - Generator Room 4 | 2 | Yes | I | N/A |  | - | PS5 - Milestone E | 0% | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 11 | 0 | 11 | 0% | 0 | 0 | 0
PS5-03-19 - FZ-19 - Power Generation Building - Battery Room | 1 | Yes | I | N/A | HOLD/meterial issue | - | PS5 - Milestone E | 0% | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 11 | 0 | 11 | 0% | 0 | 0 | 6 | PS5-03-RDH-1901/1902/1903 not arrived
PS5-03-20 - FZ-20 - Emergency Diesel Generator Enclosure | 1 | Yes | I | N/A |  | 2026-08-07 00:00:00 | PS5 - Milestone C | 100% | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 11 | 9 | 2 | 82% | 0 | 0 | 0
PS5-03-21 - FZ-21 - Power Generation Building - Air Handling Unit | 3 | Yes | I | N/A |  | - | PS5 - Milestone E | 0% | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 11 | 0 | 11 | 0% | 0 | 0 | 0
PS5-03-22 - FZ-G1 - Guard House | 5 | No | E,I | N/A |  | - | PS5 - Milestone I | 0% | 0 | 3 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 22 | 0 | 22 | 0% | 0 | 0 | 0
PS5-03-23 - FZ-E1 to E3 - EITS Building | [5 empty] | - |  | 99% | 0 | 0 | 0 | 96 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 96 | 95 | 1 | 99% | 0 | 0 | 0
PS5-03-24 - FZ - Office and Facilities Building | 5 | No | I | N/A |  | - | PS5 - Milestone I | 0% | 0 | 0 | 0 | 131 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 131 | 0 | 131 | 0% | 0 | 0 | 0
PS5-03-25 - FZ - Workshop & Warehouse | 5 | No | I | N/A |  | - | PS5 - Milestone I | 0% | 0 | 0 | 0 | 131 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 131 | 0 | 131 | 0% | 0 | 0 | 0
PS5-04-01 - Office Building PCS System | [5 empty] | - |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0% | [14 empty] | 3 | 0 | 3 | 0% | 0 | 0 | 0
PS5-04-02 - Office Building SIS/FGS System | 5 | No | I | N/A |  | - | PS5 - Milestone E | 0% | 0 | 0 | 0 | 79 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 79 | 0 | 79 | 0% | 0 | 0 | 0
PS5-04-03 - 33kV ICSS System | [5 empty] | - |  | 93% | 0 | 13 | 0 | 5 | 0 | 0 | 0 | 65 | 64 | 98% | [14 empty] | 83 | 77 | 6 | 93% | 0 | 0 | 0
PS5-04-04 - 33kV PCS System | [5 empty] | - |  | 95% | 0 | 69 | 0 | 325 | 0 | 0 | 0 | 9 | 9 | 100% | [14 empty] | 403 | 382 | 21 | 95% | 0 | 0 | 0
PS5-04-05 - 33kV SIS/FGS System | [5 empty] | - |  | 88% | 0 | 177 | 0 | 276 | 0 | 0 | 0 | 19 | 19 | 100% | [14 empty] | 472 | 416 | 56 | 88% | 0 | 0 | 0
PS5-05-01 - Emergency Diesel Generator Package | 1 | Yes | E,I,M,P | complete |  | PARTIAL(22-08-2026) | PS5 - Milestone C | 100% | 0 | 77 | 0 | 42 | 6 | 3 | 0 | 0 | 0 | - | [14 empty] | 128 | 113 | 15 | 88% | 0 | 0 | 0
PS5-05-02 - Emergency Diesel Generator Package (UCP) | 1 | Yes | E,I | N/A |  | COMPLETE | PS5 - Milestone C | 100% | 0 | 58 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 72 | 62 | 10 | 86% | 0 | 0 | 0
PS5-06-01 - AC UPS - EITS Building | [5 empty] | - |  | 70% | 0 | 154 | 0 | 19 | 0 | 0 | 0 | 12 | 12 | 100% | [14 empty] | 185 | 129 | 56 | 70% | 0 | 0 | 0
PS5-06-02 - AC UPS - Power Generator Building | 1 | Yes | E,I | N/A | 2026-08-24 | COMPLETE | PS5 - Milestone B | 100% | 0 | 89 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 97 | 72 | 25 | 74% | 0 | 0 | 0
PS5-06-03 - AC UPS - Office & Facilities Building | 5 | No | E | N/A |  | - | PS5 - Milestone I | 0% | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 9 | 0 | 9 | 0% | 0 | 0 | 0
PS5-06-04 - AC UPS - Guard House | 5 | No | E | N/A |  | - | PS5 - Milestone I | 0% | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 4 | 0 | 4 | 0% | 0 | 0 | 0
PS5-06-05 - AC UPS - Workshop & Warehouse | 5 | No | E | N/A |  | - | PS5 - Milestone I | 0% | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 7 | 0 | 7 | 0% | 0 | 0 | 0
PS5-08-01 - PAGA | 3 | Partially | T | N/A |  | - | PS5 - Milestone F | 5% | 0 | 71 | 0 | 0 | 0 | 0 | 0 | 728 | 57 | 8% | [14 empty] | 799 | 60 | 739 | 8% | 0 | 0 | 0
PS5-08-03 - Telephone | 4 | No | T | N/A |  | - | PS5 - Milestone F | 11% | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 142 | 4 | 3% | [14 empty] | 161 | 4 | 157 | 2% | 0 | 0 | 0
PS5-08-04 - Hotline | [5 empty] | - |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0% | [14 empty] | 6 | 0 | 6 | 0% | 0 | 0 | 0
PS5-08-07 - Multi-Channel Voice Recorder | [5 empty] | - |  | 0% | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0% | [14 empty] | 4 | 0 | 4 | 0% | 0 | 0 | 0
PS5-08-11 - Corporate LAN (SIE) | 3 | Yes | E | N/A |  | - | PS5 - Milestone C | 25% | 0 | 31 | 0 | 3 | 0 | 0 | 0 | 54 | 41 | 76% | [14 empty] | 88 | 55 | 33 | 62% | 0 | 0 | 0
PS5-08-12 - Corporate Wireless LAN (SIE) | 3 | No | T | N/A |  | - | PS5 - Milestone C | 0% | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 134 | 6 | 4% | [14 empty] | 155 | 6 | 149 | 4% | 0 | 0 | 0
PS5-08-13 - Safety Data Network (SII SP3 SAF) | 3 | No | T | N/A |  | - | PS5 - Milestone C | 0% | 0 | 15 | 0 | 13 | 0 | 0 | 0 | 70 | 47 | 67% | [14 empty] | 98 | 69 | 29 | 70% | 0 | 0 | 0
PS5-08-14 - Industrial Data Network (SII SP1) | 4 | No | T | N/A |  | - | PS5 - Milestone C | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0% | [14 empty] | 16 | 0 | 16 | 0% | 0 | 0 | 0
PS5-08-15 - Security Data Network (SII SP3 SEC) | 4 | No | T | N/A |  | - | PS5 - Milestone C | 0% | 0 | 32 | 0 | 11 | 0 | 0 | 0 | 76 | 39 | 51% | [14 empty] | 119 | 59 | 60 | 50% | 0 | 0 | 0
PS5-08-23 - VHF Trunk Radio System | 4 | Yes | T | N/A |  | - | PS5 - Milestone F | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103 | 12 | 12% | [14 empty] | 103 | 12 | 91 | 12% | 0 | 0 | 0
PS5-08-34 - Satphone | 4 | Yes | T | N/A |  | - | PS5 - Milestone F | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0% | [14 empty] | 20 | 0 | 20 | 0% | 0 | 0 | 0
PS5-08-35 - Optical Transport Network | [5 empty] | - |  | 80% | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 46 | 39 | 85% | [14 empty] | 61 | 49 | 12 | 80% | 0 | 0 | 0
PS5-08-36 - Pipeline FO Cable & EPRS | 3 | No | T | N/A |  | - | PS5 - Milestone C | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0% | [14 empty] | 6 | 0 | 6 | 0% | 0 | 0 | 0
PS5-08-51 - Entertainment | 4 | No | T | N/A |  | - | PS5 - Milestone I | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0% | [14 empty] | 60 | 0 | 60 | 0% | 0 | 0 | 0
PS5-08-52 - Process & Security CCTV | 4 | Yes | E,T | N/A |  | - | PS5 - Milestone F | 0% | 0 | 81 | 0 | 0 | 0 | 0 | 0 | 198 | 27 | 14% | [14 empty] | 279 | 27 | 252 | 10% | 0 | 0 | 0
PS5-08-55 - Videoconference | [5 empty] | - |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0% | [14 empty] | 5 | 0 | 5 | 0% | 0 | 0 | 0
PS5-08-61 - Meteocean | 4 | No | T | N/A |  | - | PS5 - Milestone F | 0% | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 33 | 0 | 0% | [14 empty] | 36 | 0 | 36 | 0% | 0 | 0 | 0
PS5-08-71 - Structured Cabling (CAT6) | 4 | Yes | T | N/A |  | - | PS5 - Milestone C | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 412 | 36 | 9% | [14 empty] | 412 | 36 | 376 | 9% | 0 | 0 | 0
PS5-08-72 - Structured Cabling (FO) | 3 | Yes | T | N/A |  | - | PS5 - Milestone C | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 4 | 25% | [14 empty] | 16 | 4 | 12 | 25% | 0 | 0 | 0
PS5-08-81 - Guard tour | [5 empty] | - |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0% | [14 empty] | 12 | 0 | 12 | 0% | 0 | 0 | 0
PS5-08-82 - Key Management | [5 empty] | - |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0% | [14 empty] | 6 | 0 | 6 | 0% | 0 | 0 | 0
PS5-08-83 - Perimeter & Pipeline intrusion detection system | 4 | No | T | N/A |  | - | PS5 - Milestone I | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0% | [14 empty] | 9 | 0 | 9 | 0% | 0 | 0 | 0
PS5-08-85 - Access Control, POB & e-Mustering | 4 | Yes | E,T | N/A |  | - | PS5 - Milestone F | 10% | 0 | 34 | 0 | 41 | 0 | 0 | 0 | 721 | 57 | 8% | [14 empty] | 796 | 97 | 699 | 12% | 0 | 0 | 0
PS5-08-86 - Integrated Security Management System | [5 empty] | - |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0% | [14 empty] | 16 | 0 | 16 | 0% | 0 | 0 | 0
PS5-08-92 - Telecom Mast | [5 empty] | - |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0% | [14 empty] | 2 | 0 | 2 | 0% | 0 | 0 | 0
PS5-08-93 - Telecom Monitoring System | 4 | No | T | N/A |  | - | PS5 - Milestone F | 0% | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 0% | [14 empty] | 6 | 2 | 4 | 33% | 0 | 0 | 0
PS5-09-01 - HVAC for Office and Facilities building | 5 | No | H,I | 2026-12-15 00:00:00 |  | - | PS5 - Milestone I | 0% | 0 | 0 | 19 | 39 | 1 | 1 | 0 | 0 | 0 | - | [14 empty] | 60 | 0 | 60 | 0% | 0 | 0 | 0
PS5-09-02 - HVAC for Guard House | 5 | No | E | N/A |  | - | PS5 - Milestone I | 0% | 0 | 5 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | - | [14 empty] | 6 | 0 | 6 | 0% | 0 | 0 | 0
PS5-09-03 - HVAC for Generator Building | 2 | Yes | E,H,I,M,T | 2026-10-10 00:00:00 |  | - | PS5 - Milestone D | 2% | 0 | 385 | 94 | 646 | 6 | 1 | 0 | 5 | 0 | 0% | [14 empty] | 1137 | 19 | 1118 | 2% | 0 | 0 | 0
PS5-09-04 - HVAC for Workshop & Warehouse | 5 | No | H,I | 2026-12-20 00:00:00 |  | - | PS5 - Milestone I | 0% | 0 | 0 | 12 | 28 | 1 | 1 | 0 | 0 | 0 | - | [14 empty] | 42 | 0 | 42 | 0% | 0 | 0 | 0
PS5-09-05 - HVAC for EITS Building | 1 | Yes | H,M | 2026-10-11 00:00:00 |  | PARTIAL | PS5 - Milestone A | 80% | 0 | 102 | 72 | 92 | 20 | 1 | 0 | 7 | 7 | 100% | [14 empty] | 294 | 276 | 18 | 94% | 0 | 0 | 3 | HVAC METERIAL ARIVED-17-08-26
PS5-0H-01 - HIPPS | [5 empty] | - |  | 71% | 0 | 11 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 28 | 20 | 8 | 71% | 0 | 0 | 0
PS5-25-01 - Export Pipeline Pig Receiver | 3 | Yes | E,I,M,P | 2026-10-25 00:00:00 |  | - | PS5 - Milestone H | 45% | 0 | 26 | 0 | 104 | 4 | 57 | 0 | 0 | 0 | - | [14 empty] | 191 | 66 | 125 | 35% | 0 | 0 | 0
PS5-25-02 - Crude Oil Export Pump A | 3 | Yes | E,I,M,P | 2026-10-26 00:00:00 |  | - | PS5 - Milestone H | 50% | 0 | 170 | 0 | 152 | 12 | 29 | 0 | 2 | 2 | 100% | [14 empty] | 365 | 136 | 229 | 37% | 0 | 0 | 0
PS5-25-03 - Crude Oil Export Pump B | 3 | Yes | E,I,M,P | 2026-10-27 00:00:00 |  | - | PS5 - Milestone H | 50% | 0 | 154 | 0 | 142 | 12 | 29 | 0 | 0 | 0 | - | [14 empty] | 337 | 116 | 221 | 34% | 0 | 0 | 0
PS5-25-04 - Crude Oil Export Pump C | 3 | Yes | E,I,M,P | 2026-10-28 00:00:00 |  | - | PS5 - Milestone H | 47% | 0 | 154 | 0 | 142 | 12 | 29 | 0 | 0 | 0 | - | [14 empty] | 337 | 110 | 227 | 33% | 0 | 0 | 0
PS5-25-05 - Crude Oil Export Pumps Bypass | 3 | Yes | E,I,P | 2026-10-28 00:00:00 |  | - | PS5 - Milestone H | 35% | 0 | 10 | 0 | 37 | 0 | 14 | 0 | 0 | 0 | - | [14 empty] | 61 | 17 | 44 | 28% | 0 | 0 | 0
PS5-25-06 - Crude Oil Export Pumps Discharge | 3 | Yes | E,I,P | 2026-10-29 00:00:00 |  | - | PS5 - Milestone H | 38% | 0 | 11 | 0 | 38 | 0 | 24 | 0 | 0 | 0 | - | [14 empty] | 73 | 21 | 52 | 29% | 0 | 0 | 0
PS5-25-07 - Export Pipeline Pig Launcher | 3 | Yes | E,I,M,P | 2026-10-29 00:00:00 |  | - | PS5 - Milestone H | 41% | 0 | 19 | 0 | 105 | 5 | 46 | 0 | 0 | 0 | - | [14 empty] | 175 | 52 | 123 | 30% | 0 | 0 | 0
PS5-28-01 - Closed Drain Header 1 | 3 | Yes | P | 2026-10-30 00:00:00 |  | - | PS5 - Milestone G | 64% | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | - | [14 empty] | 19 | 9 | 10 | 47% | 0 | 0 | 0
PS5-28-02 - Closed Drain Header 2 | 1.1 | Yes | P | 2026-09-01 00:00:00 |  | - | PS5 - Milestone E | 53% | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | - | [14 empty] | 20 | 8 | 12 | 40% | 0 | 0 | 0
PS5-28-03 - Closed Drain Drum and Pump 01 | 3 | Yes | E,I,M,P | 2026-10-31 00:00:00 |  | - | PS5 - Milestone G | 54% | 0 | 22 | 0 | 48 | 7 | 61 | 0 | 0 | 0 | - | [14 empty] | 138 | 59 | 79 | 43% | 0 | 0 | 0
PS5-28-04 - Closed Drain Drum and Pump 02 | 1.1 | Yes | E,I,M,P | 2026-09-07 00:00:00 |  | - | PS5 - Milestone E | 50% | 0 | 30 | 0 | 52 | 13 | 51 | 0 | 0 | 0 | - | [14 empty] | 146 | 57 | 89 | 39% | 0 | 0 | 4 |  |  | Mech(WAITING FOR ALIGNMENT TOOL)ARRAIVED-18-08-2026 | Mech(WAITING FOR ALIGNMENT TOOL)ARRAIVED-18-08-2026
PS5-28-05 - HP Relief Header | 2 | Yes | I,P | 2026-09-15 00:00:00 |  | - | PS5 - Milestone G | 36% | 0 | 0 | 0 | 3 | 0 | 14 | 0 | 0 | 0 | - | [14 empty] | 17 | 4 | 13 | 24% | 0 | 0 | 0
PS5-28-06 - Relief Drum and Pump | 2 | Yes | E,I,M,P | 2026-09-21 00:00:00 |  | - | PS5 - Milestone G | 53% | 0 | 10 | 0 | 28 | 8 | 41 | 0 | 0 | 0 | - | [14 empty] | 87 | 35 | 52 | 40% | 0 | 0 | 0
PS5-28-07 - Open Drains (OD2) | 3 | Yes | E,I,P | 2026-11-01 00:00:00 |  | - | PS5 - Milestone G | 68% | 0 | 4 | 0 | 8 | 0 | 274 | 0 | 0 | 0 | - | [14 empty] | 286 | 189 | 97 | 66% | 0 | 0 | 0
PS5-28-08 - Open Drain Sump and Pumps | 2 | Yes | E,I,M,P | 2026-10-03 00:00:00 |  | - | PS5 - Milestone G | 34% | 0 | 30 | 0 | 24 | 18 | 30 | 0 | 0 | 0 | - | [14 empty] | 102 | 27 | 75 | 26% | 0 | 0 | 0
PS5-28-09 - Observation Basin | 3 | Yes | P | 2026-11-03 00:00:00 |  | - | PS5 - Milestone I | 64% | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | - | [14 empty] | 15 | 9 | 6 | 60% | 0 | 0 | 0
PS5-28-10 - Oil Skimmer Package | 3 | Yes | E,I,M | 2026-11-03 00:00:00 |  | - | PS5 - Milestone I | 9% | 0 | 14 | 0 | 2 | 4 | 0 | 0 | 0 | 0 | - | [14 empty] | 20 | 1 | 19 | 5% | 0 | 0 | 0
PS5-28-11 - Open Drain Interceptor | 3 | Yes | E,I,M,P | 2026-10-20 00:00:00 |  | - | PS5 - Milestone I | 46% | 0 | 4 | 0 | 9 | 2 | 9 | 0 | 0 | 0 | - | [14 empty] | 24 | 6 | 18 | 25% | 0 | 0 | 0
PS5-28-12 - Open Drains (OD3) | 3 | Yes | P | 2026-10-21 00:00:00 |  | - | PS5 - Milestone I | 63% | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | - | [14 empty] | 44 | 27 | 17 | 61% | 0 | 0 | 0
PS5-28-13 - Seal Oil Drain Drum & Pump A | 3 | Yes | E,I,M,P | 2026-10-15 00:00:00 |  | - | PS5 - Milestone H | 43% | 0 | 13 | 0 | 31 | 7 | 40 | 0 | 0 | 0 | - | [14 empty] | 91 | 30 | 61 | 33% | 0 | 0 | 0
PS5-28-14 - Seal Oil Drain Drum & Pump B | 3 | Yes | E,I,M,P | 2026-09-15 00:00:00 |  | - | PS5 - Milestone H | 43% | 0 | 13 | 0 | 31 | 7 | 40 | 0 | 0 | 0 | - | [14 empty] | 91 | 30 | 61 | 33% | 0 | 0 | 0
PS5-28-15 - Seal Oil Drain Drum & Pump C | 3 | Yes | E,I,M,P | 2026-09-15 00:00:00 |  | - | PS5 - Milestone H | 43% | 0 | 13 | 0 | 31 | 7 | 40 | 0 | 0 | 0 | - | [14 empty] | 91 | 30 | 61 | 33% | 0 | 0 | 0
PS5-28-16 - LP Relief Header | 2 | Yes | I,P | 2026-09-16 00:00:00 |  | - | PS5 - Milestone G | 45% | 0 | 0 | 0 | 3 | 0 | 14 | 0 | 0 | 0 | - | [14 empty] | 17 | 5 | 12 | 29% | 0 | 0 | 0
PS5-28-17 - Reinjection Pump | 2 | Yes | E,I,M,P | 2026-10-02 00:00:00 |  | - | PS5 - Milestone H | 43% | 0 | 31 | 0 | 51 | 14 | 29 | 0 | 0 | 0 | - | [14 empty] | 125 | 38 | 87 | 30% | 0 | 0 | 0
PS5-50-01 - Water Well Submersible Pumps (3100) | 4 | Yes | E,I,M,P | 2026-09-18 00:00:00 |  | - | PS5 - Milestone I | 35% | 0 | 9 | 0 | 16 | 2 | 15 | 0 | 0 | 0 | - | [14 empty] | 42 | 10 | 32 | 24% | 0 | 0 | 0
PS5-50-02 - Water Well Submersible Pumps (3200) | 4 | Yes | E,I,M,P | 2026-09-18 00:00:00 |  | - | PS5 - Milestone I | 35% | 0 | 9 | 0 | 16 | 2 | 15 | 0 | 0 | 0 | - | [14 empty] | 42 | 10 | 32 | 24% | 0 | 0 | 0
PS5-50-03 - Water Pre-Treatment Package | 2 | Yes | E,I,M,P | 2026-10-06 00:00:00 |  | - | PS5 - Milestone F | 29% | 0 | 2 | 0 | 9 | 2 | 18 | 0 | 0 | 0 | - | [14 empty] | 31 | 7 | 24 | 23% | 0 | 0 | 0
PS5-53-01 - Utility Water / Storage Tank | 2 | Yes | E,I,M,P | 2026-10-08 00:00:00 |  | - | PS5 - Milestone C | 52% | 0 | 9 | 0 | 15 | 3 | 31 | 0 | 0 | 0 | - | [14 empty] | 58 | 24 | 34 | 41% | 0 | 0 | 0
PS5-53-02 - Water Distribution Pump A/B | 2 | Yes | E,I,M,P | 2026-10-06 00:00:00 |  | - | PS5 - Milestone E | 34% | 0 | 18 | 0 | 11 | 8 | 10 | 0 | 0 | 0 | - | [14 empty] | 47 | 12 | 35 | 26% | 0 | 0 | 0
PS5-53-03 - Water Softener Package | 2 | Yes | E,I,M,P | 2026-10-08 00:00:00 |  | - | PS5 - Milestone E | 35% | 0 | 2 | 0 | 4 | 3 | 17 | 0 | 0 | 0 | - | [14 empty] | 26 | 6 | 20 | 23% | 0 | 0 | 0
PS5-53-04 - Water Treatment Purification Package | 2 | No | E,I,M,P | 2026-10-08 00:00:00 |  | - | PS5 - Milestone F | 0% | 0 | 12 | 0 | 13 | 3 | 3 | 0 | 0 | 0 | - | [14 empty] | 31 | 0 | 31 | 0% | 0 | 0 | 0
PS5-53-05 - Water Distribution Header | 2 | No | P | 2026-10-05 00:00:00 |  | - | PS5 - Milestone F | 69% | 0 | 0 | 0 | 0 | 1 | 60 | 0 | 0 | 0 | - | [14 empty] | 61 | 40 | 21 | 66% | 0 | 0 | 0
PS5-53-06 - Water Distribution Consumers | 4 | No | P | 2026-09-02 00:00:00 |  | - | PS5 - Milestone F | 67% | 0 | 0 | 0 | 0 | 1 | 41 | 0 | 0 | 0 | - | [14 empty] | 42 | 26 | 16 | 62% | 0 | 0 | 0
PS5-60-01 - Power Generation Package A | 1 | Yes | E,I,M,P | 2026-08-18 00:00:00 | 2026-08-27 | PARTIAL | PS5 - Milestone B | 98% | 0 | 132 | 0 | 68 | 22 | 24 | 0 | 0 | 0 | - | [14 empty] | 246 | 188 | 58 | 76% | 0 | 2 | 0
PS5-60-02 - Power Gen Package A (UCP) | 1 | Yes | E,I | N/A | 2026-08-20 | COMPLETE | PS5 - Milestone B | 100% | 0 | 9 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 64 | 51 | 13 | 80% | 0 | 0 | 0
PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | 1 | Yes | E,I,T | N/A | 2026-08-27 | PARTIAL | PS5 - Milestone B | 71% | 0 | 28 | 0 | 4 | 0 | 0 | 0 | 3 | 1 | 33% | [14 empty] | 35 | 17 | 18 | 49% | 0 | 3 | 3 | CPP will execute the job as per SI for telecom , waiting material from CPY | Grounding cable missing 1x240mm2
PS5-60-04 - Power Generation Package B | 1 | Yes | E,I,M,P | 2026-08-17 00:00:00 | 2026-08-24 | PARTIAL | PS5 - Milestone B | 97% | 0 | 126 | 0 | 51 | 14 | 24 | 0 | 0 | 0 | - | [14 empty] | 215 | 165 | 50 | 77% | 0 | 0 | 0
PS5-60-05 - Power Gen Package B (UCP) | 1 | Yes | E,I,T | N/A | 2026-08-22 | PARTIAL | PS5 - Milestone B | 92% | 0 | 9 | 0 | 55 | 0 | 0 | 0 | 9 | 4 | 44% | [14 empty] | 73 | 52 | 21 | 71% | 0 | 0 | 4 | CPP will execute the job as per SI for telecom , waiting material from CPY
PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | 1 | Yes | E,I,T | N/A | 2026-08-30 | - | PS5 - Milestone B | 73% | 0 | 26 | 0 | 4 | 0 | 0 | 0 | 3 | 1 | 33% | [14 empty] | 33 | 16 | 17 | 48% | 0 | 2 | 3 | CPP will execute the job as per SI for telecom , waiting material from CPY | 1x240mm2 cable not available.CPP Supply
PS5-60-07 - Power Generation Package C | 1.1 | Yes | E,I,M,P | 2026-08-20 00:00:00 |  | - | PS5 - Milestone D | 76% | 0 | 126 | 0 | 51 | 13 | 24 | 0 | 0 | 0 | - | [14 empty] | 214 | 136 | 78 | 64% | 0 | 0 | 2 | PS5-60-BI-0016C-CCO4 6T X 0.75 IS/OS FL RTD 131m
PS5-60-08 - Power Gen Package C (UCP) | 1.1 | Yes | E,I,T | N/A |  | - | PS5 - Milestone D | 48% | 0 | 9 | 0 | 55 | 0 | 0 | 0 | 9 | 4 | 44% | [14 empty] | 73 | 26 | 47 | 36% | 0 | 0 | 2 | 1)Waiting delivery of CAT6A material by EACOP
PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs | 1.1 | Yes | E,I,T | N/A |  | - | PS5 - Milestone D | 46% | 0 | 28 | 0 | 4 | 0 | 0 | 0 | 3 | 1 | 33% | [14 empty] | 35 | 11 | 24 | 31% | 0 | 2 | 0 | CPP will execute the job as per SI for telecom , waiting material from CPY | PS5-60-IH-0001C-CG01 1x240mm2 grounding cable 40m
PS5-60-10 - Power Generation Package D | 1.1 | Yes | E,I,M,P,T | 2026-08-20 00:00:00 |  | - | PS5 - Milestone D | 70% | 0 | 132 | 0 | 64 | 14 | 24 | 0 | 13 | 6 | 46% | [14 empty] | 247 | 140 | 107 | 57% | 0 | 2 | 2 | 1) Waiting delivery of CAT6A material by EACOP 2) PS5-60-BI-0016D-CCO4 6T X 0.75 IS/OS FL RTD 121m
PS5-60-11 - Power Gen Package D (UCP) | 1.1 | Yes | E,I,T | N/A |  | - | PS5 - Milestone D | 48% | 0 | 9 | 0 | 55 | 0 | 0 | 0 | 9 | 4 | 44% | [14 empty] | 73 | 25 | 48 | 34% | 0 | 0 | 2 | Waiting delivery of CAT6A material by EACOP
PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs | 1.1 | Yes | E,I,T | N/A | 2026-08-26 | PARTIAL | PS5 - Milestone D | 73% | 0 | 26 | 0 | 4 | 0 | 0 | 0 | 3 | 1 | 33% | [14 empty] | 33 | 16 | 17 | 48% | 0 | 2 | 0 | CPP will execute the job as per SI for telecom , waiting material from CPY | PS5-60-IH-0001D-CG01 1x240mm2 grounding cable, 35m
PS5-60-13 - Power Generation Package E | 2 | Yes | E,I,M,P | 2026-08-28 00:00:00 |  | - | PS5 - Milestone D | 53% | 0 | 126 | 0 | 51 | 13 | 24 | 0 | 0 | 0 | - | [14 empty] | 214 | 89 | 125 | 42% | 0 | 0 | 0
PS5-60-14 - Power Gen Package E (UCP) | 2 | Yes | E,I,T | N/A |  | - | PS5 - Milestone D | 29% | 0 | 9 | 0 | 55 | 0 | 0 | 0 | 9 | 4 | 44% | [14 empty] | 73 | 15 | 58 | 21% | 0 | 0 | 0
PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs | 2 | Yes | E,I,T | N/A |  | - | PS5 - Milestone D | 42% | 0 | 28 | 0 | 4 | 0 | 0 | 0 | 3 | 1 | 33% | [14 empty] | 35 | 10 | 25 | 29% | 0 | 0 | 0
PS5-60-16 - Power Generation Package F | 2 | Yes | E,I,M,P,T | 2026-08-28 00:00:00 |  | - | PS5 - Milestone D | 51% | 0 | 132 | 0 | 64 | 14 | 24 | 0 | 13 | 6 | 46% | [14 empty] | 247 | 101 | 146 | 41% | 0 | 0 | 0
PS5-60-17 - Power Gen Package F (UCP) | 2 | Yes | E,I,T | N/A |  | - | PS5 - Milestone D | 38% | 0 | 9 | 0 | 55 | 0 | 0 | 0 | 9 | 4 | 44% | [14 empty] | 73 | 20 | 53 | 27% | 0 | 0 | 0
PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs | 2 | Yes | E,I,T | N/A |  | - | PS5 - Milestone D | 23% | 0 | 26 | 0 | 4 | 0 | 0 | 0 | 3 | 1 | 33% | [14 empty] | 33 | 5 | 28 | 15% | 0 | 0 | 0
PS5-60-19 - Power Generation Package G | 2 | Yes | E,I,M,P | 2026-08-29 00:00:00 |  | - | PS5 - Milestone E | 50% | 0 | 126 | 0 | 51 | 14 | 24 | 0 | 0 | 0 | - | [14 empty] | 215 | 86 | 129 | 40% | 0 | 0 | 0
PS5-60-20 - Power Gen Package G (UCP) | 2 | Yes | E,I,T | N/A |  | - | PS5 - Milestone E | 36% | 0 | 9 | 0 | 55 | 0 | 0 | 0 | 7 | 3 | 43% | [14 empty] | 71 | 18 | 53 | 25% | 0 | 0 | 0
PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs | 2 | Yes | E,I,T | N/A |  | - | PS5 - Milestone E | 29% | 0 | 28 | 0 | 4 | 0 | 0 | 0 | 3 | 1 | 33% | [14 empty] | 35 | 7 | 28 | 20% | 0 | 0 | 0
PS5-60-22 - Power Gen Master UCP | 1 | Yes | E,I,T | N/A | 2026-09-04 | - | PS5 - Milestone B | 62% | 0 | 84 | 0 | 69 | 0 | 0 | 0 | 13 | 6 | 46% | [14 empty] | 166 | 72 | 94 | 43% | 0 | 0 | 6 | CPP will execute the job as per SI for telecom , waiting material from CPY
PS5-60-23 - Instrument Air Distribution lines | 1 | Yes | P | 2026-08-18 00:00:00 | 2026-08-27 | - | PS5 - Milestone B | 75% | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | - | [14 empty] | 11 | 7 | 4 | 64% | 0 | 0 | 0
PS5-60-24 - Cooling Water Tank & Pump | 1 | Yes | E,I,M,P | 2026-08-26 00:00:00 | 2026-08-27 | - | PS5 - Milestone E | 87% | 0 | 10 | 0 | 11 | 5 | 47 | 0 | 0 | 0 | - | [14 empty] | 73 | 59 | 14 | 81% | 0 | 0 | 3 | PS5-60-LIT-4301 not arrived. |  | Mechanical-PUMP ALIGNMENT TOOL NOT AVAILABLE-ARRAIVED-18-08-2026 | Mechanical-PUMP ALIGNMENT TOOL NOT AVAILABLE-ARRAIVED-18-08-2026
PS5-60-25 - Cooling Water Maintenance Tank & Return Pump | 1 | Yes | E,I,M,P | 2026-08-26 00:00:00 | 2026-08-27 | - | PS5 - Milestone E | 86% | 0 | 10 | 0 | 11 | 5 | 42 | 0 | 0 | 0 | - | [14 empty] | 68 | 53 | 15 | 78% | 0 | 0 | 3 | PS5-60-LIT-4401 not arrived |  | Mechanical-PUMP ALIGNMENT TOOL NOT AVAILABLE-ARRAIVED-18-08-2026 | Mechanical-PUMP ALIGNMENT TOOL NOT AVAILABLE-ARRAIVED-18-08-2026
PS5-60-26 - Instrument Air Compressor Skid | 1 | Yes | E,I,M,P | 2026-08-18 00:00:00 | 2026-08-20 | COMPLETE | PS5 - Milestone B | 100% | 0 | 15 | 0 | 4 | 8 | 16 | 0 | 0 | 0 | - | [14 empty] | 43 | 30 | 13 | 70% | 0 | 0 | 0
PS5-60-27 - Compressed Air Starting Skid | 1 | Yes | E,I,M,P | 2026-08-18 00:00:00 | 2026-08-20 | PARTIAL | PS5 - Milestone B | 96% | 0 | 12 | 0 | 4 | 10 | 16 | 0 | 0 | 0 | - | [14 empty] | 42 | 27 | 15 | 64% | 0 | 0 | 0
PS5-60-28 - Air Receiver A & Air Regulator A | 1 | Yes | I,P | 2026-08-18 00:00:00 | 2026-08-20 | PARTIAL | PS5 - Milestone B | 92% | 0 | 0 | 0 | 5 | 1 | 11 | 0 | 0 | 0 | - | [14 empty] | 17 | 13 | 4 | 76% | 0 | 0 | 0
PS5-60-29 - Air Receiver B & Air Regulator B | 1 | Yes | I,P | 2026-08-22 00:00:00 | 2026-08-22 | PARTIAL | PS5 - Milestone B | 92% | 0 | 0 | 0 | 5 | 1 | 11 | 0 | 0 | 0 | - | [14 empty] | 17 | 12 | 5 | 71% | 0 | 0 | 0
PS5-60-30 - Air Receiver C & Air Regulator C | 1.1 | Yes | I,P | 2026-08-21 00:00:00 | 2026-08-28 | - | PS5 - Milestone D | 92% | 0 | 0 | 0 | 5 | 1 | 11 | 0 | 0 | 0 | - | [14 empty] | 17 | 12 | 5 | 71% | 0 | 0 | 0
PS5-60-31 - Air Receiver D & Air Regulator D | 1.1 | Yes | I,P | 2026-08-21 00:00:00 | 2026-08-28 | - | PS5 - Milestone D | 92% | 0 | 0 | 0 | 5 | 1 | 11 | 0 | 0 | 0 | - | [14 empty] | 17 | 12 | 5 | 71% | 0 | 0 | 0
PS5-60-32 - Air Receiver E & Air Regulator E | 2 | Yes | I,P | 2026-08-29 00:00:00 |  | - | PS5 - Milestone D | 46% | 0 | 0 | 0 | 5 | 1 | 11 | 0 | 0 | 0 | - | [14 empty] | 17 | 6 | 11 | 35% | 0 | 0 | 0
PS5-60-33 - Air Receiver F & Air Regulator F | 2 | Yes | I,P | 2026-08-30 00:00:00 |  | - | PS5 - Milestone D | 46% | 0 | 0 | 0 | 5 | 1 | 11 | 0 | 0 | 0 | - | [14 empty] | 17 | 6 | 11 | 35% | 0 | 0 | 0
PS5-60-34 - Air Receiver G & Air Regulator G | 2 | Yes | I,P | 2026-08-30 00:00:00 |  | - | PS5 - Milestone E | 54% | 0 | 0 | 0 | 5 | 1 | 11 | 0 | 0 | 0 | - | [14 empty] | 17 | 8 | 9 | 47% | 0 | 0 | 0
PS5-60-35 - Injector Tip Cooling Module A | 1 | Yes | E,I,M,P | 2026-08-17 00:00:00 |  | COMPLETE | PS5 - Milestone B | 100% | 0 | 13 | 0 | 4 | 11 | 19 | 0 | 0 | 0 | - | [14 empty] | 47 | 36 | 11 | 77% | 0 | 0 | 0
PS5-60-36 - Injector Tip Cooling Module B | 1 | Yes | E,I,M,P | 2026-08-17 00:00:00 |  | COMPLETE | PS5 - Milestone B | 100% | 0 | 13 | 0 | 4 | 6 | 19 | 0 | 0 | 0 | - | [14 empty] | 42 | 36 | 6 | 86% | 0 | 0 | 0
PS5-60-37 - Injector Tip Cooling Module C | 1.1 | Yes | E,I,M,P | 2026-09-01 00:00:00 |  | - | PS5 - Milestone D | 85% | 0 | 13 | 0 | 4 | 7 | 19 | 0 | 0 | 0 | - | [14 empty] | 43 | 31 | 12 | 72% | 0 | 0 | 0
PS5-60-38 - Injector Tip Cooling Module D | 1.1 | Yes | E,I,M,P | 2026-09-01 00:00:00 |  | - | PS5 - Milestone D | 85% | 0 | 13 | 0 | 4 | 7 | 19 | 0 | 0 | 0 | - | [14 empty] | 43 | 31 | 12 | 72% | 0 | 0 | 0
PS5-60-39 - Injector Tip Cooling Module E | 2 | Yes | E,I,M,P | 2026-09-25 00:00:00 |  | - | PS5 - Milestone D | 61% | 0 | 13 | 0 | 4 | 6 | 19 | 0 | 0 | 0 | - | [14 empty] | 42 | 21 | 21 | 50% | 0 | 0 | 0
PS5-60-40 - Injector Tip Cooling Module F | 2 | Yes | E,I,M,P | 2026-09-26 00:00:00 |  | - | PS5 - Milestone D | 59% | 0 | 13 | 0 | 4 | 7 | 19 | 0 | 0 | 0 | - | [14 empty] | 43 | 21 | 22 | 49% | 0 | 0 | 0
PS5-60-41 - Injector Tip Cooling Module G | 2 | Yes | E,I,M,P | 2026-09-27 00:00:00 |  | - | PS5 - Milestone E | 56% | 0 | 13 | 0 | 4 | 7 | 19 | 0 | 0 | 0 | - | [14 empty] | 43 | 20 | 23 | 47% | 0 | 0 | 0
PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A | 1 | Yes | E,I,M,P | 2026-08-17 00:00:00 |  | COMPLETE | PS5 - Milestone B | 100% | 0 | 5 | 0 | 4 | 5 | 21 | 0 | 0 | 0 | - | [14 empty] | 35 | 31 | 4 | 89% | 0 | 0 | 0
PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B | 1 | Yes | E,I,M,P | 2026-08-17 00:00:00 |  | COMPLETE | PS5 - Milestone B | 100% | 0 | 5 | 0 | 4 | 4 | 21 | 0 | 0 | 0 | - | [14 empty] | 34 | 31 | 3 | 91% | 0 | 0 | 0
PS5-60-44 - Oil Mist Separator Skid PS5-60-VS-9100C | 1.1 | Yes | E,I,M,P | 2026-09-01 00:00:00 |  | - | PS5 - Milestone D | 89% | 0 | 5 | 0 | 4 | 4 | 21 | 0 | 0 | 0 | - | [14 empty] | 34 | 24 | 10 | 71% | 0 | 0 | 0
PS5-60-45 - Oil Mist Separator Skid PS5-60-VS-9100D | 1.1 | Yes | E,I,M,P | 2026-09-02 00:00:00 |  | - | PS5 - Milestone D | 89% | 0 | 5 | 0 | 4 | 4 | 21 | 0 | 0 | 0 | - | [14 empty] | 34 | 24 | 10 | 71% | 0 | 0 | 0
PS5-60-46 - Oil Mist Separator Skid PS5-60-VS-9100E | 2 | Yes | E,I,M,P | 2026-09-28 00:00:00 |  | - | PS5 - Milestone D | 74% | 0 | 5 | 0 | 4 | 4 | 21 | 0 | 0 | 0 | - | [14 empty] | 34 | 20 | 14 | 59% | 0 | 0 | 0
PS5-60-47 - Oil Mist Separator Skid PS5-60-VS-9100F | 2 | Yes | E,I,M,P | 2026-09-29 00:00:00 |  | - | PS5 - Milestone D | 74% | 0 | 5 | 0 | 4 | 4 | 21 | 0 | 0 | 0 | - | [14 empty] | 34 | 20 | 14 | 59% | 0 | 0 | 0
PS5-60-48 - Oil Mist Separator Skid PS5-60-VS-9100G | 2 | Yes | E,I,M,P | 2026-10-01 00:00:00 |  | - | PS5 - Milestone E | 70% | 0 | 5 | 0 | 4 | 4 | 21 | 0 | 0 | 0 | - | [14 empty] | 34 | 19 | 15 | 56% | 0 | 0 | 0
PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | 1 | Yes | E,I,M,P,T | 2026-08-19 00:00:00 | 2026-08-20 | PARTIAL | PS5 - Milestone B | 94% | 0 | 8 | 0 | 12 | 4 | 17 | 0 | 3 | 1 | 33% | [14 empty] | 44 | 36 | 8 | 82% | 0 | 0 | 1 | CPP will execute the job as per SI for telecom , waiting material from CPY
PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | 1 | Yes | E,I,M,P,T | 2026-08-20 00:00:00 | 2026-08-26 | PARTIAL | PS5 - Milestone B | 94% | 0 | 8 | 0 | 12 | 4 | 17 | 0 | 3 | 1 | 33% | [14 empty] | 44 | 33 | 11 | 75% | 0 | 0 | 1 | CPP will execute the job as per SI for telecom , waiting material from CPY
PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | 1.1 | Yes | E,I,M,P,T | 2026-09-02 00:00:00 |  | - | PS5 - Milestone D | 74% | 0 | 8 | 0 | 12 | 4 | 17 | 0 | 3 | 1 | 33% | [14 empty] | 44 | 30 | 14 | 68% | 0 | 0 | 0 | CPP will execute the job as per SI for telecom , waiting material from CPY
PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | 1.1 | Yes | E,I,M,P,T | 2026-09-03 00:00:00 |  | - | PS5 - Milestone D | 74% | 0 | 8 | 0 | 12 | 4 | 17 | 0 | 3 | 1 | 33% | [14 empty] | 44 | 26 | 18 | 59% | 0 | 0 | 0 | CPP will execute the job as per SI for telecom , waiting material from CPY
PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E | 2 | Yes | E,I,M,P,T | 2026-10-02 00:00:00 |  | - | PS5 - Milestone D | 57% | 0 | 8 | 0 | 12 | 4 | 17 | 0 | 3 | 0 | 0% | [14 empty] | 44 | 21 | 23 | 48% | 0 | 0 | 0
PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F | 2 | Yes | E,I,M,P,T | 2026-10-03 00:00:00 |  | - | PS5 - Milestone D | 57% | 0 | 8 | 0 | 12 | 4 | 17 | 0 | 3 | 0 | 0% | [14 empty] | 44 | 21 | 23 | 48% | 0 | 0 | 0
PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G | 2 | Yes | E,I,M,P,T | 2026-10-04 00:00:00 |  | - | PS5 - Milestone E | 51% | 0 | 8 | 0 | 12 | 4 | 17 | 0 | 3 | 0 | 0% | [14 empty] | 44 | 19 | 25 | 43% | 0 | 0 | 0
PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | 1 | Yes | E,I,M,P | 2026-08-20 00:00:00 | 2026-08-26 | PARTIAL | PS5 - Milestone B | 94% | 0 | 39 | 0 | 9 | 9 | 19 | 0 | 0 | 0 | - | [14 empty] | 76 | 62 | 14 | 82% | 0 | 0 | 2 | Cables pending due to PIT location issue, colliding with pipes |  | THERMAL INSULATION | THERMAL INSULATION
PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | 1 | Yes | E,I,T | N/A | 2026-08-22 | PARTIAL | PS5 - Milestone B | 88% | 0 | 14 | 0 | 24 | 0 | 0 | 0 | 3 | 1 | 33% | [14 empty] | 41 | 31 | 10 | 76% | 0 | 2 | 1 | CPP will execute the job as per SI for telecom , waiting material from CPY | 1x25mm2 cable not available.CPP Supply
PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | 1 | Yes | E,I,M,P | 2026-08-21 00:00:00 | 2026-08-26 | PARTIAL | PS5 - Milestone B | 94% | 0 | 39 | 0 | 9 | 6 | 19 | 0 | 0 | 0 | - | [14 empty] | 73 | 63 | 10 | 86% | 0 | 0 | 2 | Cables pending due to PIT location issue, colliding with pipes |  | THERMAL INSULATION | THERMAL INSULATION
PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | 1 | Yes | E,I,T | N/A | 2026-08-24 | PARTIAL | PS5 - Milestone B | 88% | 0 | 14 | 0 | 24 | 0 | 0 | 0 | 3 | 1 | 33% | [14 empty] | 41 | 30 | 11 | 73% | 0 | 2 | 1 | CPP will execute the job as per SI for telecom , waiting material from CPY | 1x25mm2 cable not available.CPP Supply
PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | 1.1 | Yes | E,I,M,P | 2026-09-04 00:00:00 |  | - | PS5 - Milestone D | 67% | 0 | 39 | 0 | 9 | 6 | 19 | 0 | 0 | 0 | - | [14 empty] | 73 | 47 | 26 | 64% | 0 | 0 | 0 | Cables pending due to PIT location issue, colliding with pipes
PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | 1.1 | Yes | E,I,T | N/A |  | - | PS5 - Milestone D | 74% | 0 | 14 | 0 | 24 | 0 | 0 | 0 | 3 | 1 | 33% | [14 empty] | 41 | 25 | 16 | 61% | 0 | 2 | 1 | CPP will execute the job as per SI for telecom , waiting material from CPY | PS5-60-IN-0002C-CG01 1X25mm2 grounding cable 130m
PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | 1.1 | Yes | E,I,M,P | 2026-09-04 00:00:00 |  | - | PS5 - Milestone D | 66% | 0 | 39 | 0 | 9 | 6 | 19 | 0 | 0 | 0 | - | [14 empty] | 73 | 44 | 29 | 60% | 0 | 0 | 0 | Cables pending due to PIT location issue, colliding with pipes
PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | 1.1 | Yes | E,I,T | N/A |  | - | PS5 - Milestone D | 38% | 0 | 14 | 0 | 24 | 0 | 0 | 0 | 3 | 1 | 33% | [14 empty] | 41 | 13 | 28 | 32% | 0 | 2 | 1 | CPP will execute the job as per SI for telecom , waiting material from CPY | PS5-60-IN-0002D-CG01 1x25mm2 grounding cable 120m
PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | 2 | Yes | E,I,M,P | 2026-10-01 00:00:00 |  | - | PS5 - Milestone D | 43% | 0 | 39 | 0 | 9 | 6 | 19 | 0 | 0 | 0 | - | [14 empty] | 73 | 30 | 43 | 41% | 0 | 0 | 0
PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | 2 | Yes | E,I,T | N/A |  | - | PS5 - Milestone D | 26% | 0 | 14 | 0 | 24 | 0 | 0 | 0 | 3 | 0 | 0% | [14 empty] | 41 | 9 | 32 | 22% | 0 | 0 | 0
PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | 2 | Yes | E,I,M,P | 2026-10-02 00:00:00 |  | - | PS5 - Milestone D | 39% | 0 | 39 | 0 | 9 | 6 | 19 | 0 | 0 | 0 | - | [14 empty] | 73 | 27 | 46 | 37% | 0 | 0 | 0
PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | 2 | Yes | E,I,T | N/A |  | - | PS5 - Milestone D | 26% | 0 | 14 | 0 | 24 | 0 | 0 | 0 | 3 | 0 | 0% | [14 empty] | 41 | 9 | 32 | 22% | 0 | 0 | 0
PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | 2 | Yes | E,I,M,P | 2026-10-04 00:00:00 |  | - | PS5 - Milestone E | 36% | 0 | 39 | 0 | 9 | 6 | 19 | 0 | 0 | 0 | - | [14 empty] | 73 | 25 | 48 | 34% | 0 | 0 | 0
PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | 2 | Yes | E,I,T | N/A |  | - | PS5 - Milestone E | 26% | 0 | 14 | 0 | 24 | 0 | 0 | 0 | 3 | 0 | 0% | [14 empty] | 41 | 9 | 32 | 22% | 0 | 0 | 0
PS5-60-70 - Engine A Cooling system | 1 | Yes | E,I,M,P | 2026-08-19 00:00:00 | 2026-08-22 | PARTIAL | PS5 - Milestone B | 99% | 0 | 11 | 0 | 17 | 20 | 42 | 0 | 0 | 0 | - | [14 empty] | 90 | 69 | 21 | 77% | 0 | 0 | 0
PS5-60-71 - Engine B Cooling system | 1 | Yes | E,I,M,P | 2026-08-20 00:00:00 | 2026-08-22 | PARTIAL | PS5 - Milestone B | 99% | 0 | 11 | 0 | 17 | 8 | 42 | 0 | 0 | 0 | - | [14 empty] | 78 | 69 | 9 | 88% | 0 | 0 | 0
PS5-60-72 - Engine C Cooling system | 1.1 | Yes | E,I,M,P | 2026-09-04 00:00:00 |  | - | PS5 - Milestone D | 83% | 0 | 11 | 0 | 17 | 8 | 42 | 0 | 0 | 0 | - | [14 empty] | 78 | 59 | 19 | 76% | 0 | 0 | 0
PS5-60-73 - Engine D Cooling system | 1.1 | Yes | E,I,M,P | 2026-09-05 00:00:00 |  | - | PS5 - Milestone D | 83% | 0 | 11 | 0 | 17 | 8 | 42 | 0 | 0 | 0 | - | [14 empty] | 78 | 59 | 19 | 76% | 0 | 0 | 0
PS5-60-74 - Engine E Cooling system | 2 | Yes | E,I,M,P | 2026-10-05 00:00:00 |  | - | PS5 - Milestone D | 66% | 0 | 11 | 0 | 17 | 8 | 42 | 0 | 0 | 0 | - | [14 empty] | 78 | 47 | 31 | 60% | 0 | 0 | 0
PS5-60-75 - Engine F Cooling system | 2 | Yes | E,I,M,P | 2026-10-05 00:00:00 |  | - | PS5 - Milestone D | 64% | 0 | 11 | 0 | 17 | 8 | 42 | 0 | 0 | 0 | - | [14 empty] | 78 | 46 | 32 | 59% | 0 | 0 | 0
PS5-60-76 - Engine G Cooling system | 2 | Yes | E,I,M,P | 2026-10-06 00:00:00 |  | - | PS5 - Milestone E | 44% | 0 | 11 | 0 | 17 | 8 | 42 | 0 | 0 | 0 | - | [14 empty] | 78 | 32 | 46 | 41% | 0 | 0 | 0
PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | 1 | Yes | E,M | complete | 2026-08-31 | - | PS5 - Milestone D | 67% | 0 | 345 | 0 | 10 | 9 | 0 | 0 | 35 | 28 | 80% | [14 empty] | 399 | 256 | 143 | 64% | 0 | 0 | 4 |  | PS5-61-IV-0005A/5B Not arrived.
PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010) | 3 | Yes | E,M | complete |  | - | PS5 - Milestone G | 29% | 0 | 88 | 0 | 1 | 2 | 0 | 0 | 7 | 6 | 86% | [14 empty] | 98 | 40 | 58 | 41% | 0 | 0 | 0
PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011) | 3 | Yes | E,M | complete |  | - | PS5 - Milestone G | 29% | 0 | 86 | 0 | 1 | 2 | 0 | 0 | 9 | 6 | 67% | [14 empty] | 98 | 37 | 61 | 38% | 0 | 0 | 0
PS5-61-04 - 0.4kV Switchboard Office & Facilities Building (PS5-61-IK-0005) | 1 | No | E | N/A | HOLD/meterial issue | - | PS5 - Milestone I | 0% | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 35 | 0 | 35 | 0% | 0 | 18 | 0 |  | all the cables cannot be laid due to pending excavation to office/building area.
PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | 1 | Yes | E | N/A | 2026-08-24 | COMPLETE | PS5 - Milestone B | 100% | 0 | 155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 155 | 115 | 40 | 74% | 0 | 0 | 0
PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | 1 | Yes | E | N/A | 2026-09-10 | - | PS5 - Milestone D | 55% | 0 | 130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 130 | 52 | 78 | 40% | 0 | 0 | 16 | Cannot terminate the cables due to busbar panel issues and cannot close the static/conformity ITRs of the panel. Cables cannot be terminated on transformer side due to gland plate issue
PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | 2 | Yes | E,M | complete |  | - | PS5 - Milestone A | 99% | 0 | 232 | 0 | 108 | 2 | 0 | 0 | 16 | 16 | 100% | [14 empty] | 358 | 271 | 87 | 76% | 0 | 0 | 0
PS5-61-08 - Electrical Control System | 2 | Yes | E | N/A |  | - | PS5 - Milestone C | 0% | 0 | 195 | 0 | 9 | 0 | 0 | 0 | 35 | 34 | 97% | [14 empty] | 239 | 157 | 82 | 66% | 0 | 0 | 0
PS5-61-09 - Outdoor Power Distribution Board - PS5-61-IG-0014 | 2 | Yes | E | N/A |  | - | PS5 - Milestone G | 5% | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 34 | 1 | 33 | 3% | 0 | 0 | 0
PS5-61-10 - Outdoor Valves Distribution Board - PS5-61-IG-0042 | 2 | Yes | E | N/A |  | - | PS5 - Milestone F | 25% | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 15 | 1 | 14 | 7% | 0 | 0 | 0
PS5-61-11 - Outdoor Valves Distribution Board - PS5-61-IG-0043 | 1.1 | Yes | E | N/A |  | - | PS5 - Milestone F | 25% | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 15 | 1 | 14 | 7% | 0 | 0 | 0
PS5-61-12 - EITS 33kV Bld. Normal Auxiliary DP - PS5-61-IG-0008 | [5 empty] | - |  | 32% | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 25 | 8 | 17 | 32% | 0 | 0 | 0
PS5-61-13 - Power Distribution Board Office Building - PS5-61-IG-0020 | 5 | No | E | N/A |  | - | PS5 - Milestone I | 0% | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 5 | 0 | 5 | 0% | 0 | 0 | 0
PS5-61-14 - Power Distribution Board Workshop & Warehouse - PS5-61-IG-0009 | 4 | No | E | N/A |  | - | PS5 - Milestone I | 0% | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 5 | 0 | 5 | 0% | 0 | 0 | 0
PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | 2 | Yes | E | N/A |  | - | PS5 - Milestone G | 6% | 0 | 94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 94 | 4 | 90 | 4% | 0 | 0 | 0
PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | 2 | Yes | E | N/A |  | - | PS5 - Milestone G | 4% | 0 | 102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 102 | 3 | 99 | 3% | 0 | 0 | 0
PS5-62-03 - Outdoor Emergency Lighting DB - PS5-05-IG-0004 | 2 | Yes | E | N/A |  | - | PS5 - Milestone G | 25% | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 15 | 1 | 14 | 7% | 0 | 0 | 0
PS5-62-04 - Outdoor Emergency Lighting DB - PS5-05-IG-0006 | 2 | Yes | E | N/A |  | - | PS5 - Milestone G | 25% | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 24 | 1 | 23 | 4% | 0 | 0 | 0
PS5-62-05 - Guard House Emergency L&SP DB - PS5-05-IG-0007 | 4 | No | E | N/A |  | - | PS5 - Milestone I | 0% | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 36 | 0 | 36 | 0% | 0 | 0 | 0
PS5-62-06 - CRO Generator Building Emergency Lighting DB - PS5-05-IG-0025 | 1.1 | Yes | E | N/A |  | - | PS5 - Milestone B | 5% | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 36 | 1 | 35 | 3% | 0 | 0 | 0
PS5-62-07 - CRO Generator Electrical Building Emergency Lighting DB - PS5-05-IG-0026 | 1.1 | Yes | E | N/A |  | - | PS5 - Milestone B | 12% | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 34 | 2 | 32 | 6% | 0 | 0 | 0
PS5-62-08 - Outdoor Normal Lighting DB - PS5-61-IG-0006 | 2 | No | E | N/A |  | - | PS5 - Milestone G | 5% | 0 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 43 | 1 | 42 | 2% | 0 | 0 | 0
PS5-62-09 - Outdoor Normal Lighting DB - PS5-61-IG-0007 | 2 | No | E | N/A |  | - | PS5 - Milestone G | 46% | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 44 | 11 | 33 | 25% | 0 | 0 | 0
PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015 | 1.1 | Yes | E | N/A |  | - | PS5 - Milestone B | 3% | 0 | 67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 67 | 1 | 66 | 1% | 0 | 0 | 0
PS5-62-11 - CRO Generator Electrical Building Normal L&SP DB - PS5-61-IG-0016 | 1.1 | Yes | E | N/A |  | - | PS5 - Milestone B | 5% | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 37 | 1 | 36 | 3% | 0 | 0 | 0
PS5-62-12 - EITS 33kV Bld. Emergency L&SP DP - PS5-05-IG-0003 | [5 empty] | - |  | 73% | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 26 | 19 | 7 | 73% | 0 | 0 | 0
PS5-62-13 - EITS 33kV Bld. Normal L&SP DP - PS5-61-IG-0003 | [5 empty] | - |  | 74% | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 34 | 25 | 9 | 74% | 0 | 0 | 0
PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-0002 | 5 | No | E | N/A |  | - | PS5 - Milestone I | 3% | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 32 | 1 | 31 | 3% | 0 | 0 | 0
PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002 | 5 | No | E | N/A |  | - | PS5 - Milestone I | 0% | 0 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 47 | 0 | 47 | 0% | 0 | 0 | 0
PS5-62-16 - Guard Hut A Normal L&SP DB - PS5-61-IG-0111 | 5 | No | E | N/A |  | - | PS5 - Milestone I | 0% | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 7 | 0 | 7 | 0% | 0 | 0 | 0
PS5-62-17 - Guard Hut B Normal L&SP DB - PS5-61-IG-0112 | 5 | No | E | N/A |  | - | PS5 - Milestone I | 0% | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 7 | 0 | 7 | 0% | 0 | 0 | 0
PS5-62-18 - Workshop & Warehouse Normal L&SP DB - PS5-61-IG-0004 | 5 | No | E | N/A |  | - | PS5 - Milestone I | 0% | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 5 | 0 | 5 | 0% | 0 | 0 | 0
PS5-62-19 - Workshop & Warehouse Emergency L&SP DB - PS5-05-IG-0101 | 5 | No | E | N/A |  | - | PS5 - Milestone I | 0% | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 5 | 0 | 5 | 0% | 0 | 0 | 0
PS5-62-20 - Office Building Normal L&SP DB - PS5-61-IG-0010 | 5 | No | E | N/A |  | - | PS5 - Milestone I | 0% | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 11 | 0 | 11 | 0% | 0 | 0 | 0
PS5-63-01 - Electrical Earthing | 1 | Yes | E | N/A |  | - | PS5 - Milestone A | 24% | 0 | 69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 69 | 16 | 53 | 23% | 0 | 40 | 0 |  | 18 ITRs for lightning, 22 ITRs for grounding cannot be closed due to material issues.
PS5-63-02 - Electrical Earthing - Office and Facilities building | 4 | No | E | N/A |  | - | PS5 - Milestone I | 0% | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 5 | 0 | 5 | 0% | 0 | 0 | 0
PS5-63-03 - Electrical Earthing - Generator Building | 1 | Yes | E | N/A | 2026-08-24 | PARTIAL | PS5 - Milestone B | 50% | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 5 | 2 | 3 | 40% | 0 | 2 | 0 |  | lightning cannot be completed due to materials
PS5-63-04 - Electrical Earthing - EITS Building | [5 empty] | - |  | 100% | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 28 | 28 | 0 | 100% | 0 | 0 | 0
PS5-63-05 - Electrical Earthing - Guard Hut A & B | 4 | No | E | N/A |  | - | PS5 - Milestone I | 0% | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 9 | 0 | 9 | 0% | 0 | 0 | 0
PS5-63-06 - Electrical Earthing - Guard House | 4 | No | E | N/A |  | - | PS5 - Milestone I | 0% | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 5 | 0 | 5 | 0% | 0 | 0 | 0
PS5-63-07 - Electrical Earthing - Workshop & Warehouse | 4 | No | E | N/A |  | - | PS5 - Milestone I | 0% | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 5 | 0 | 5 | 0% | 0 | 0 | 0
PS5-71-01 - CFO Storage Tank Feed Heater | 2 | No | E,I,M,P | 2026-10-03 00:00:00 |  | - | PS5 - Milestone H | 37% | 0 | 45 | 0 | 82 | 3 | 34 | 0 | 0 | 0 | - | [14 empty] | 164 | 57 | 107 | 35% | 0 | 0 | 0
PS5-71-02 - CFO Allocation Metering Package | 2 | No | E,I,M,P | 2026-10-03 00:00:00 |  | - | PS5 - Milestone H | 47% | 0 | 2 | 0 | 12 | 3 | 14 | 0 | 0 | 0 | - | [14 empty] | 31 | 8 | 23 | 26% | 0 | 0 | 0
PS5-71-03 - CFO Allocation Metering Package (UCP) | [5 empty] | - |  | 47% | 0 | 11 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 15 | 7 | 8 | 47% | 0 | 0 | 0
PS5-71-04 - CFO Storage Tank | 2 | No | E,I,M,P | 2026-10-04 00:00:00 |  | - | PS5 - Milestone H | 39% | 0 | 34 | 0 | 70 | 3 | 50 | 0 | 0 | 0 | - | [14 empty] | 157 | 51 | 106 | 32% | 0 | 0 | 0
PS5-71-05 - CFO Transfer Pump A/B | 2 | No | E,I,M,P | 2026-10-05 00:00:00 |  | - | PS5 - Milestone H | 36% | 0 | 21 | 0 | 45 | 11 | 18 | 0 | 0 | 0 | - | [14 empty] | 95 | 25 | 70 | 26% | 0 | 0 | 0
PS5-71-06 - Crude Fuel Separation Module | 1.1 | No | E,I,M,P | 2026-09-05 00:00:00 |  | - | PS5 - Milestone H | 48% | 0 | 3 | 0 | 35 | 6 | 26 | 0 | 0 | 0 | - | [14 empty] | 70 | 30 | 40 | 43% | 0 | 0 | 22 | PS5-71-BI-0001A-CC01 12P X 0.75 OS FL RTD 20m PS5-71-BI-0001B-CC01 12P X 0.75 OS FL RTD 20m PS5-71-BI-0008B-CC01 12P X 0.75 IS/OS FL RTD 170 PS5-71-BI-0008B-CC02 12P X 0.75 IS/OS FL RTD 170 PS5-71-BI-0011A-CC01 6T X 2.5 OS FL RTD 20 PS5-71-BI-0011A-CC02 6T X 2.5 OS FL RTD 20 PS5-71-BI-0011A-CC03 6P X 0.75 OS FL RTD 20 PS5-71-BI-0011A-CC05 6T X 2.5 OS FL RTD 20 PS5-71-BI-0011B-CC01 6T X 2.5 OS FL RTD 20 PS5-71-BI-0011B-CC02 6T X 2.5 OS FL RTD 20 PS5-71-BI-0011B-CC05 6T X 2.5 OS FL RTD 20 |  | Piping FM & Reins(TP 378 EQUIPMENT NOT AVAILABLE) | Piping FM & Reins(TP 378 EQUIPMENT NOT AVAILABLE)
PS5-71-07 - Crude Fuel Separation Module (UCP) | 1.1 | No | E,I,T | N/A |  | - | PS5 - Milestone H | 21% | 0 | 71 | 0 | 62 | 0 | 0 | 0 | 5 | 2 | 40% | [14 empty] | 138 | 24 | 114 | 17% | 0 | 0 | 54 | cable drum not available for 24 cables, added in Rev09of cable schedule. CPP will execute the job as per SI for telecom , waiting material from CPY
PS5-71-08 - CFO Pre-Pressure Modules | 1.1 | No | E,I,M,P | 2026-08-31 00:00:00 |  | - | PS5 - Milestone H | 70% | 0 | 30 | 0 | 36 | 3 | 19 | 0 | 0 | 0 | - | [14 empty] | 88 | 59 | 29 | 67% | 0 | 0 | 3 | PS5-71-BI-0003-CC04 6P X 0.75 OS FL RTD 20m PS5-71-BI-0003-CC01 engineering issue.
PS5-71-09 - CFO Pre-Pressure Modules (UCP) | 1.1 | No | E,I,T | N/A | 2026-08-27 | PARTIAL | PS5 - Milestone H | 95% | 0 | 12 | 0 | 21 | 0 | 0 | 0 | 3 | 1 | 33% | [14 empty] | 36 | 21 | 15 | 58% | 0 | 0 | 0
PS5-71-12 - CFO Service Tank | 2 | No | E,I,M,P | 2026-10-06 00:00:00 |  | - | PS5 - Milestone H | 41% | 0 | 39 | 0 | 85 | 2 | 34 | 0 | 0 | 0 | - | [14 empty] | 160 | 52 | 108 | 32% | 0 | 0 | 0
PS5-71-13 - CFO Service Pump A/B | 2 | No | E,I,M,P | 2026-10-06 00:00:00 |  | - | PS5 - Milestone H | 36% | 0 | 21 | 0 | 35 | 11 | 18 | 0 | 0 | 0 | - | [14 empty] | 85 | 22 | 63 | 26% | 0 | 0 | 0
PS5-71-14 - Diesel Fuel Transfer and Dispensing Station | 2 | No | E,I,M,P | 2026-10-07 00:00:00 |  | - | PS5 - Milestone F | 44% | 0 | 14 | 0 | 7 | 10 | 11 | 0 | 0 | 0 | - | [14 empty] | 42 | 12 | 30 | 29% | 0 | 0 | 0
PS5-71-15 - Diesel Fuel Storage Tank | 2 | Yes | E,I,M,P | 2026-10-10 00:00:00 |  | - | PS5 - Milestone F | 51% | 0 | 12 | 0 | 36 | 3 | 21 | 0 | 0 | 0 | - | [14 empty] | 72 | 29 | 43 | 40% | 0 | 0 | 0
PS5-71-16 - Diesel Fuel Supply Pump A/B | 2 | Yes | E,I,M,P | 2026-10-07 00:00:00 |  | - | PS5 - Milestone F | 30% | 0 | 18 | 0 | 13 | 12 | 11 | 0 | 0 | 0 | - | [14 empty] | 54 | 12 | 42 | 22% | 0 | 0 | 0
PS5-71-17 - Diesel Fuel Distribution Header | 2 | Yes | I,P | 2026-10-07 00:00:00 |  | - | PS5 - Milestone F | 52% | 0 | 0 | 0 | 19 | 0 | 20 | 0 | 0 | 0 | - | [14 empty] | 39 | 16 | 23 | 41% | 0 | 0 | 0
PS5-71-18 - Diesel Separator Module | 1 | Yes | E,I,M,P | 2026-08-19 00:00:00 | 2026-08-29 | - | PS5 - Milestone F | 64% | 0 | 5 | 0 | 31 | 16 | 22 | 0 | 0 | 0 | - | [14 empty] | 74 | 34 | 40 | 46% | 0 | 0 | 4 | PS5-71-BI-0002-CC01, 155m ,Cable type:12P X 0.75 OS FL RTD PS5-71-BI-0009-CC01, 175m, Cable type:6T X 2.5 IS/OS FR
PS5-71-19 - Diesel Separator Module (UCP) | 1 | Yes | E,I,T | N/A | 2026-09-10 | - | PS5 - Milestone F | 32% | 0 | 20 | 0 | 27 | 0 | 0 | 0 | 5 | 1 | 20% | [14 empty] | 52 | 16 | 36 | 31% | 0 | 0 | 8 | PS5-71-BE-0005-CL01 4C+E 16 210m , PS5-71-BE-0005-CL02 2C+E 2.5 210m , PS5-71-BE-0005-CL03 4C+E 6 210m PS5-71-BE-0005-CL04 2C+E 2.5 210m. These cables were added in latest revision, not available.
PS5-71-20 - Diesel Fuel Day Tank | 1 | Yes | E,I,M,P | 2026-08-20 00:00:00 | 2026-08-29 | - | PS5 - Milestone B | 84% | 0 | 7 | 0 | 35 | 3 | 22 | 0 | 0 | 0 | - | [14 empty] | 67 | 46 | 21 | 69% | 0 | 0 | 6 | 6 ITRS pending due to LIT 1201/1202 (not arrived yet)
PS5-71-21 - Diesel Transfer Pump A/B | 1 | Yes | E,I,M,P | 2026-08-19 00:00:00 | 2026-08-29 | - | PS5 - Milestone B | 84% | 0 | 21 | 0 | 30 | 12 | 16 | 0 | 0 | 0 | - | [14 empty] | 79 | 52 | 27 | 66% | 0 | 2 | 3 | PS5-71-21-0331 - Test Package - CPP Item Nipple and 1/2 Flange not available at site. CPY/EPS Supply Item PS5-71-FIT-0019 – SRN-01997, awaiting collection from vendor by MLC (airfreight). PS5-71-FIT-0019 not arrived.
PS5-71-22 - Diesel Fuel Pre Pressure Module | 1 | Yes | E,I,M,P | 2026-08-20 00:00:00 | 2026-08-29 | - | PS5 - Milestone B | 98% | 0 | 18 | 0 | 28 | 13 | 31 | 0 | 0 | 0 | - | [14 empty] | 90 | 65 | 25 | 72% | 0 | 0 | 0
PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | 1 | Yes | E,I,T | N/A | 2026-08-28 | - | PS5 - Milestone B | 68% | 0 | 12 | 0 | 24 | 0 | 0 | 0 | 3 | 1 | 33% | [14 empty] | 39 | 20 | 19 | 51% | 0 | 0 | 4 | CPP will execute the job as per SI for telecom , waiting material from CPY PS5-71-BI-0005-CC01 12P X 0.75 OS FL RTD cable not available PS5-71-BI-0005-CC02 Engineering Issue
PS5-74-01 - N2 Generation Skid | 2 | Yes | E,I,M,P | complete |  | - | PS5 - Milestone F | 38% | 0 | 9 | 0 | 2 | 4 | 3 | 0 | 0 | 0 | - | [14 empty] | 18 | 3 | 15 | 17% | 0 | 0 | 0
PS5-74-02 - N2 Generation Skid (UCP) | 2 | Yes | E,I | N/A |  | - | PS5 - Milestone F | 22% | 0 | 7 | 0 | 18 | 1 | 0 | 0 | 0 | 0 | - | [14 empty] | 26 | 2 | 24 | 8% | 0 | 0 | 0
PS5-74-03 - Nitrogen Receiver | 2 | Yes | I,M,P | 2026-10-08 00:00:00 |  | - | PS5 - Milestone F | 50% | 0 | 0 | 0 | 5 | 3 | 19 | 0 | 0 | 0 | - | [14 empty] | 27 | 10 | 17 | 37% | 0 | 0 | 0
PS5-74-04 - Nitrogen Distribution Header | 2 | Yes | I,P | 2026-10-08 00:00:00 |  | - | PS5 - Milestone F | 25% | 0 | 0 | 0 | 10 | 1 | 11 | 0 | 0 | 0 | - | [14 empty] | 22 | 5 | 17 | 23% | 0 | 0 | 0
PS5-75-01 - DRA Injection Package | 3 | No | E,I,M,P | 2026-11-01 00:00:00 |  | - | PS5 - Milestone G | 20% | 0 | 13 | 0 | 24 | 3 | 18 | 0 | 0 | 0 | - | [14 empty] | 58 | 6 | 52 | 10% | 0 | 0 | 0
PS5-75-02 - Biocide Injection Package | 3 | Yes | E,I,M,P | 2026-09-16 00:00:00 |  | - | PS5 - Milestone G | 42% | 0 | 13 | 0 | 17 | 8 | 17 | 0 | 0 | 0 | - | [14 empty] | 55 | 13 | 42 | 24% | 0 | 0 | 0
PS5-75-03 - Corrosion Inhibitor Injection Package | 3 | Yes | E,I,M,P | 2026-09-17 00:00:00 |  | - | PS5 - Milestone G | 36% | 0 | 13 | 0 | 15 | 8 | 18 | 0 | 0 | 0 | - | [14 empty] | 54 | 12 | 42 | 22% | 0 | 0 | 0
PS5-78-01 - Lifting and handling equipment | 3 | Partially | E,M | 2026-09-18 00:00:00 |  | PARTIAL(05-03-2026) | PS5 - Milestone E | 55% | 0 | 16 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | - | [14 empty] | 43 | 27 | 16 | 63% | 0 | 0 | 0
PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | 3 | Yes | E,I,M | complete |  | - | PS5 - Milestone H | 4% | 0 | 103 | 0 | 5 | 1 | 0 | 0 | 0 | 0 | - | [14 empty] | 109 | 3 | 106 | 3% | 0 | 0 | 0
PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | 3 | Yes | E,I,M | complete |  | - | PS5 - Milestone H | 4% | 0 | 106 | 0 | 5 | 1 | 0 | 0 | 0 | 0 | - | [14 empty] | 112 | 3 | 109 | 3% | 0 | 0 | 0
PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | 3 | Yes | E,I,M | complete |  | - | PS5 - Milestone H | 4% | 0 | 103 | 0 | 5 | 1 | 0 | 0 | 0 | 0 | - | [14 empty] | 109 | 3 | 106 | 3% | 0 | 0 | 0
PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | 3 | Yes | E,I,M | complete |  | - | PS5 - Milestone H | 5% | 0 | 97 | 0 | 5 | 1 | 0 | 0 | 0 | 0 | - | [14 empty] | 103 | 3 | 100 | 3% | 0 | 0 | 0
PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | 3 | Yes | E,I,M | complete |  | - | PS5 - Milestone H | 4% | 0 | 100 | 0 | 5 | 1 | 0 | 0 | 0 | 0 | - | [14 empty] | 106 | 3 | 103 | 3% | 0 | 0 | 0
PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | 3 | Yes | E,I,M | complete |  | - | PS5 - Milestone H | 4% | 0 | 112 | 0 | 5 | 1 | 0 | 0 | 0 | 0 | - | [14 empty] | 118 | 3 | 115 | 3% | 0 | 0 | 0
PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | 3 | Yes | E,I,M | complete |  | - | PS5 - Milestone H | 4% | 0 | 112 | 0 | 5 | 1 | 0 | 0 | 0 | 0 | - | [14 empty] | 118 | 3 | 115 | 3% | 0 | 0 | 0
PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | 3 | Yes | E,I,M | complete |  | - | PS5 - Milestone H | 4% | 0 | 112 | 0 | 5 | 1 | 0 | 0 | 0 | 0 | - | [14 empty] | 118 | 3 | 115 | 3% | 0 | 0 | 0
PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | 3 | Yes | E,I,M | complete |  | - | PS5 - Milestone H | 4% | 0 | 112 | 0 | 5 | 1 | 0 | 0 | 0 | 0 | - | [14 empty] | 118 | 3 | 115 | 3% | 0 | 0 | 0
PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | 3 | Yes | E,I,M | complete |  | - | PS5 - Milestone H | 4% | 0 | 106 | 0 | 5 | 1 | 0 | 0 | 0 | 0 | - | [14 empty] | 112 | 3 | 109 | 3% | 0 | 0 | 0
PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | 3 | Yes | E,I,M | complete |  | - | PS5 - Milestone H | 4% | 0 | 106 | 0 | 5 | 1 | 0 | 0 | 0 | 0 | - | [14 empty] | 112 | 3 | 109 | 3% | 0 | 0 | 0
PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | 3 | Yes | E,I,M | complete |  | - | PS5 - Milestone H | 1% | 0 | 121 | 0 | 5 | 1 | 0 | 0 | 0 | 0 | - | [14 empty] | 127 | 1 | 126 | 1% | 0 | 0 | 0
PS5-82-01 - Sanitary Sewage Collection | 4 | No | P | 2026-11-11 00:00:00 |  | - | PS5 - Milestone I | 60% | 0 | 0 | 0 | 0 | 0 | 52 | 0 | 0 | 0 | - | [14 empty] | 52 | 30 | 22 | 58% | 0 | 0 | 0
PS5-82-02 - Sewage Treatment Plant Package | 4 | No | E,I,M,P | 2026-11-12 00:00:00 |  | - | PS5 - Milestone I | 17% | 0 | 6 | 0 | 3 | 4 | 4 | 0 | 0 | 0 | - | [14 empty] | 17 | 1 | 16 | 6% | 0 | 0 | 0
PS5-82-03 - Sewage Treatment Plant Package (UCP) | 4 | No | I | N/A |  | - | PS5 - Milestone I | 0% | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | - | [14 empty] | 4 | 0 | 4 | 0% | 0 | 0 | 0
PS5-82-04 - Sewage Treatment Plant Discharge Piping | 4 | No | P | 2026-11-13 00:00:00 |  | - | PS5 - Milestone I | 50% | 0 | 0 | 0 | 0 | 1 | 10 | 0 | 0 | 0 | - | [14 empty] | 11 | 4 | 7 | 36% | 0 | 0 | 0
PS5-82-05 - Office and Facilities building | 5 | No | B,E | 2026-12-31 00:00:00 |  | - | PS5 - Milestone I | 0% | 10 | 3 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | - | [14 empty] | 14 | 0 | 14 | 0% | 0 | 0 | 0
PS5-82-06 - Guard House Building | 5 | No | B,E | 2026-12-21 00:00:00 |  | - | PS5 - Milestone I | 0% | 10 | 3 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | - | [14 empty] | 14 | 0 | 14 | 0% | 0 | 0 | 0
PS5-82-07 - Guard Huts | 5 | No | B | 2026-12-11 00:00:00 |  | - | PS5 - Milestone I | 0% | 6 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | - | [14 empty] | 7 | 0 | 7 | 0% | 0 | 0 | 0
PS5-83-01 - EITS Building | 2 | Yes | E,M | complete |  | - | PS5 - Milestone A | 67% | 3 | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | - | [14 empty] | 11 | 7 | 4 | 64% | 0 | 0 | 0
PS5-84-01 - Generator Building | 2 | Yes | B,E | 2026-10-10 00:00:00 |  | - | PS5 - Milestone E | 0% | 10 | 3 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | - | [14 empty] | 14 | 0 | 14 | 0% | 0 | 0 | 0
PS5-84-02 - Workshop & Warehouse | 5 | No | B | 2026-12-16 00:00:00 |  | - | PS5 - Milestone I | 0% | 9 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | - | [14 empty] | 10 | 0 | 10 | 0% | 0 | 0 | 0
PS5-84-03 - Shelters | 4 | No | B | 2026-10-21 00:00:00 |  | - | PS5 - Milestone I | 0% | 4 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | - | [14 empty] | 5 | 0 | 5 | 0% | 0 | 0 | 0
PS5-86-01 - Shelters | 4 | No | B | 2026-10-23 00:00:00 |  | - | PS5 - Milestone I | 0% | 4 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | - | [14 empty] | 5 | 0 | 5 | 0% | 0 | 0 | 0
PS5-91-01 - Multicore cables & JB | 1 | Yes | I | N/A | 2026-08-22 | COMPLETE | PS5 - Milestone A | 100% | 0 | 0 | 0 | 194 | 0 | 0 | 0 | 0 | 0 | - | [14 empty] | 194 | 151 | 43 | 78% | 0 | 0 | 0
PS5-99-01 - Area Completion for Building area | 4 | No | B,E | 2026-11-15 00:00:00 |  | - | PS5 - Milestone I | 0% | 4 | 3 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | - | [14 empty] | 8 | 0 | 8 | 0% | 0 | 0 | 0
PS5-99-02 - Area Completion for Utility area | 3 | No | B,E | 2026-11-01 00:00:00 |  | - | PS5 - Milestone I | 0% | 2 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | - | [14 empty] | 5 | 0 | 5 | 0% | 0 | 0 | 0
PS5-99-03 - Area Completion for Power Distribution area | 2 | No | B,E | 2026-10-10 00:00:00 |  | - | PS5 - Milestone I | 0% | 2 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | - | [14 empty] | 5 | 0 | 5 | 0% | 0 | 0 | 0
PS5-99-04 - Area Completion for Process area | 2 | No | B,E | 2026-10-10 00:00:00 |  | - | PS5 - Milestone I | 0% | 6 | 4 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | - | [14 empty] | 11 | 0 | 11 | 0% | 0 | 0 | 0
PS5-99-05 - Area Completion for CFO area | 2 | No | B,E | 2026-10-10 00:00:00 |  | - | PS5 - Milestone I | 0% | 2 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | - | [14 empty] | 5 | 0 | 5 | 0% | 0 | 0 | 0
PS5-99-06 - Area Completion for Power Generation area | 2 | No | B,E | 2026-10-10 00:00:00 |  | - | PS5 - Milestone I | 0% | 2 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | - | [14 empty] | 5 | 0 | 5 | 0% | 0 | 0 | 0

## SIDMAP (hidden)
PS5-01-01 - Fire Water Jockey Pump A/B | PS5-01-01
PS5-01-02 - Fire Water Pump A | PS5-01-02
PS5-01-03 - Fire Water Pump B | PS5-01-03
PS5-01-04 - Fire Water Pump Mini Flow Recycle | PS5-01-04
PS5-01-05 - Foam Skid | PS5-01-05
PS5-01-06 - Foam Concentrate Distribution | PS5-01-06
PS5-01-07 - Fire Water Ring Main & Distribution | PS5-01-07
PS5-01-08 - PS5 Deluge Valve Skid (PS5-01-UK-6100) | PS5-01-08
PS5-01-09 - Inergen for EITS Building | PS5-01-09
PS5-01-10 - Water Mist Package | PS5-01-10
PS5-01-11 - Inergen for Power Gen Building | PS5-01-11
PS5-02-01 - Miscellaneous Safety equipment | PS5-02-01
PS5-02-02 - Portable Fire Fighting Equipments | PS5-02-02
PS5-03-01 - FZ-01 - Process Area | PS5-03-01
PS5-03-03 - FZ-03 - Buildings Area | PS5-03-03
PS5-03-04 - FZ-04 - Utilities - Diesel and Firewater Pumps Areas | PS5-03-04
PS5-03-06 - FZ-06 - Transformer Area | PS5-03-06
PS5-03-07 - FZ-07 - Pretreatment Area | PS5-03-07
PS5-03-08 - FZ-08 - Utilities - Power Generation Area - External | PS5-03-08
PS5-03-09 - FZ-09 - Power Generation Building - Engine Bay 1 | PS5-03-09
PS5-03-10 - FZ-10 - Power Generation Building - Engine Bay 2 | PS5-03-10
PS5-03-11 - FZ-11 - Power Generation Building - Engine Bay 3 | PS5-03-11
PS5-03-12 - FZ-12 - Power Generation Building - Engine Bay 4 | PS5-03-12
PS5-03-13 - FZ-13 - Power Generation Building - Instrument Air Room | PS5-03-13
PS5-03-14 - FZ-14 - Power Generation Building - Switchgear Room | PS5-03-14
PS5-03-15 - FZ-15 - Power Generation Building - Generator Room 1 | PS5-03-15
PS5-03-16 - FZ-16 - Power Generation Building - Generator Room 2 | PS5-03-16
PS5-03-17 - FZ-17 - Power Generation Building - Generator Room 3 | PS5-03-17
PS5-03-18 - FZ-18 - Power Generation Building - Generator Room 4 | PS5-03-18
PS5-03-19 - FZ-19 - Power Generation Building - Battery Room | PS5-03-19
PS5-03-20 - FZ-20 - Emergency Diesel Generator Enclosure | PS5-03-20
PS5-03-21 - FZ-21 - Power Generation Building - Air Handling Unit | PS5-03-21
PS5-03-22 - FZ-G1 - Guard House | PS5-03-22
PS5-03-23 - FZ-E1 to E3 - EITS Building | PS5-03-23
PS5-03-24 - FZ - Office and Facilities Building | PS5-03-24
PS5-03-25 - FZ - Workshop & Warehouse | PS5-03-25
PS5-04-01 - Office Building PCS System | PS5-04-01
PS5-04-02 - Office Building SIS/FGS System | PS5-04-02
PS5-04-03 - 33kV ICSS System | PS5-04-03
PS5-04-04 - 33kV PCS System | PS5-04-04
PS5-04-05 - 33kV SIS/FGS System | PS5-04-05
PS5-05-01 - Emergency Diesel Generator Package | PS5-05-01
PS5-05-02 - Emergency Diesel Generator Package (UCP) | PS5-05-02
PS5-06-01 - AC UPS - EITS Building | PS5-06-01
PS5-06-02 - AC UPS - Power Generator Building | PS5-06-02
PS5-06-03 - AC UPS - Office & Facilities Building | PS5-06-03
PS5-06-04 - AC UPS - Guard House | PS5-06-04
PS5-06-05 - AC UPS - Workshop & Warehouse | PS5-06-05
PS5-08-01 - PAGA | PS5-08-01
PS5-08-03 - Telephone | PS5-08-03
PS5-08-04 - Hotline | PS5-08-04
PS5-08-07 - Multi-Channel Voice Recorder | PS5-08-07
PS5-08-11 - Corporate LAN (SIE) | PS5-08-11
PS5-08-12 - Corporate Wireless LAN (SIE) | PS5-08-12
PS5-08-13 - Safety Data Network (SII SP3 SAF) | PS5-08-13
PS5-08-14 - Industrial Data Network (SII SP1) | PS5-08-14
PS5-08-15 - Security Data Network (SII SP3 SEC) | PS5-08-15
PS5-08-23 - VHF Trunk Radio System | PS5-08-23
PS5-08-34 - Satphone | PS5-08-34
PS5-08-35 - Optical Transport Network | PS5-08-35
PS5-08-36 - Pipeline FO Cable & EPRS | PS5-08-36
PS5-08-51 - Entertainment | PS5-08-51
PS5-08-52 - Process & Security CCTV | PS5-08-52
PS5-08-55 - Videoconference | PS5-08-55
PS5-08-61 - Meteocean | PS5-08-61
PS5-08-71 - Structured Cabling (CAT6) | PS5-08-71
PS5-08-72 - Structured Cabling (FO) | PS5-08-72
PS5-08-81 - Guard tour | PS5-08-81
PS5-08-82 - Key Management | PS5-08-82
PS5-08-83 - Perimeter & Pipeline intrusion detection system | PS5-08-83
PS5-08-85 - Access Control, POB & e-Mustering | PS5-08-85
PS5-08-86 - Integrated Security Management System | PS5-08-86
PS5-08-92 - Telecom Mast | PS5-08-92
PS5-08-93 - Telecom Monitoring System | PS5-08-93
PS5-09-01 - HVAC for Office and Facilities building | PS5-09-01
PS5-09-02 - HVAC for Guard House | PS5-09-02
PS5-09-03 - HVAC for Generator Building | PS5-09-03
PS5-09-04 - HVAC for Workshop & Warehouse | PS5-09-04
PS5-09-05 - HVAC for EITS Building | PS5-09-05
PS5-0H-01 - HIPPS | PS5-0H-01
PS5-25-01 - Export Pipeline Pig Receiver | PS5-25-01
PS5-25-02 - Crude Oil Export Pump A | PS5-25-02
PS5-25-03 - Crude Oil Export Pump B | PS5-25-03
PS5-25-04 - Crude Oil Export Pump C | PS5-25-04
PS5-25-05 - Crude Oil Export Pumps Bypass | PS5-25-05
PS5-25-06 - Crude Oil Export Pumps Discharge | PS5-25-06
PS5-25-07 - Export Pipeline Pig Launcher | PS5-25-07
PS5-28-01 - Closed Drain Header 1 | PS5-28-01
PS5-28-02 - Closed Drain Header 2 | PS5-28-02
PS5-28-03 - Closed Drain Drum and Pump 01 | PS5-28-03
PS5-28-04 - Closed Drain Drum and Pump 02 | PS5-28-04
PS5-28-05 - HP Relief Header | PS5-28-05
PS5-28-06 - Relief Drum and Pump | PS5-28-06
PS5-28-07 - Open Drains (OD2) | PS5-28-07
PS5-28-08 - Open Drain Sump and Pumps | PS5-28-08
PS5-28-09 - Observation Basin | PS5-28-09
PS5-28-10 - Oil Skimmer Package | PS5-28-10
PS5-28-11 - Open Drain Interceptor | PS5-28-11
PS5-28-12 - Open Drains (OD3) | PS5-28-12
PS5-28-13 - Seal Oil Drain Drum & Pump A | PS5-28-13
PS5-28-14 - Seal Oil Drain Drum & Pump B | PS5-28-14
PS5-28-15 - Seal Oil Drain Drum & Pump C | PS5-28-15
PS5-28-16 - LP Relief Header | PS5-28-16
PS5-28-17 - Reinjection Pump | PS5-28-17
PS5-50-01 - Water Well Submersible Pumps (3100) | PS5-50-01
PS5-50-02 - Water Well Submersible Pumps (3200) | PS5-50-02
PS5-50-03 - Water Pre-Treatment Package | PS5-50-03
PS5-53-01 - Utility Water / Storage Tank | PS5-53-01
PS5-53-02 - Water Distribution Pump A/B | PS5-53-02
PS5-53-03 - Water Softener Package | PS5-53-03
PS5-53-04 - Water Treatment Purification Package | PS5-53-04
PS5-53-05 - Water Distribution Header | PS5-53-05
PS5-53-06 - Water Distribution Consumers | PS5-53-06
PS5-60-01 - Power Generation Package A | PS5-60-01
PS5-60-02 - Power Gen Package A (UCP) | PS5-60-02
PS5-60-03 - Power Gen Package A Generator Auxiliary MCCs & DBs | PS5-60-03
PS5-60-04 - Power Generation Package B | PS5-60-04
PS5-60-05 - Power Gen Package B (UCP) | PS5-60-05
PS5-60-06 - Power Gen Package B Generator Auxiliary MCCs & DBs | PS5-60-06
PS5-60-07 - Power Generation Package C | PS5-60-07
PS5-60-08 - Power Gen Package C (UCP) | PS5-60-08
PS5-60-09 - Power Gen Package C Generator Auxiliary MCCs & DBs | PS5-60-09
PS5-60-10 - Power Generation Package D | PS5-60-10
PS5-60-11 - Power Gen Package D (UCP) | PS5-60-11
PS5-60-12 - Power Gen Package D Generator Auxiliary MCCs & DBs | PS5-60-12
PS5-60-13 - Power Generation Package E | PS5-60-13
PS5-60-14 - Power Gen Package E (UCP) | PS5-60-14
PS5-60-15 - Power Gen Package E Generator Auxiliary MCCs & DBs | PS5-60-15
PS5-60-16 - Power Generation Package F | PS5-60-16
PS5-60-17 - Power Gen Package F (UCP) | PS5-60-17
PS5-60-18 - Power Gen Package F Generator Auxiliary MCCs & DBs | PS5-60-18
PS5-60-19 - Power Generation Package G | PS5-60-19
PS5-60-20 - Power Gen Package G (UCP) | PS5-60-20
PS5-60-21 - Power Gen Package G Generator Auxiliary MCCs & DBs | PS5-60-21
PS5-60-22 - Power Gen Master UCP | PS5-60-22
PS5-60-23 - Instrument Air Distribution lines | PS5-60-23
PS5-60-24 - Cooling Water Tank & Pump | PS5-60-24
PS5-60-25 - Cooling Water Maintenance Tank & Return Pump | PS5-60-25
PS5-60-26 - Instrument Air Compressor Skid | PS5-60-26
PS5-60-27 - Compressed Air Starting Skid | PS5-60-27
PS5-60-28 - Air Receiver A & Air Regulator A | PS5-60-28
PS5-60-29 - Air Receiver B & Air Regulator B | PS5-60-29
PS5-60-30 - Air Receiver C & Air Regulator C | PS5-60-30
PS5-60-31 - Air Receiver D & Air Regulator D | PS5-60-31
PS5-60-32 - Air Receiver E & Air Regulator E | PS5-60-32
PS5-60-33 - Air Receiver F & Air Regulator F | PS5-60-33
PS5-60-34 - Air Receiver G & Air Regulator G | PS5-60-34
PS5-60-35 - Injector Tip Cooling Module A | PS5-60-35
PS5-60-36 - Injector Tip Cooling Module B | PS5-60-36
PS5-60-37 - Injector Tip Cooling Module C | PS5-60-37
PS5-60-38 - Injector Tip Cooling Module D | PS5-60-38
PS5-60-39 - Injector Tip Cooling Module E | PS5-60-39
PS5-60-40 - Injector Tip Cooling Module F | PS5-60-40
PS5-60-41 - Injector Tip Cooling Module G | PS5-60-41
PS5-60-42 - Oil Mist Separator Skid PS5-60-VS-9100A | PS5-60-42
PS5-60-43 - Oil Mist Separator Skid PS5-60-VS-9100B | PS5-60-43
PS5-60-44 - Oil Mist Separator Skid PS5-60-VS-9100C | PS5-60-44
PS5-60-45 - Oil Mist Separator Skid PS5-60-VS-9100D | PS5-60-45
PS5-60-46 - Oil Mist Separator Skid PS5-60-VS-9100E | PS5-60-46
PS5-60-47 - Oil Mist Separator Skid PS5-60-VS-9100F | PS5-60-47
PS5-60-48 - Oil Mist Separator Skid PS5-60-VS-9100G | PS5-60-48
PS5-60-49 - Lube Oil Separator Module PS5-60-UO-81100A | PS5-60-49
PS5-60-50 - Lube Oil Separator Module PS5-60-UO-81100B | PS5-60-50
PS5-60-51 - Lube Oil Separator Module PS5-60-UO-81100C | PS5-60-51
PS5-60-52 - Lube Oil Separator Module PS5-60-UO-81100D | PS5-60-52
PS5-60-53 - Lube Oil Separator Module PS5-60-UO-81100E | PS5-60-53
PS5-60-54 - Lube Oil Separator Module PS5-60-UO-81100F | PS5-60-54
PS5-60-55 - Lube Oil Separator Module PS5-60-UO-81100G | PS5-60-55
PS5-60-56 - Fuel Conditioning Module PS5-60-UZ-8900A | PS5-60-56
PS5-60-57 - Fuel Conditioning Module PS5-60-UZ-8900A (UCP) | PS5-60-57
PS5-60-58 - Fuel Conditioning Module PS5-60-UZ-8900B | PS5-60-58
PS5-60-59 - Fuel Conditioning Module PS5-60-UZ-8900B (UCP) | PS5-60-59
PS5-60-60 - Fuel Conditioning Module PS5-60-UZ-8900C | PS5-60-60
PS5-60-61 - Fuel Conditioning Module PS5-60-UZ-8900C (UCP) | PS5-60-61
PS5-60-62 - Fuel Conditioning Module PS5-60-UZ-8900D | PS5-60-62
PS5-60-63 - Fuel Conditioning Module PS5-60-UZ-8900D (UCP) | PS5-60-63
PS5-60-64 - Fuel Conditioning Module PS5-60-UZ-8900E | PS5-60-64
PS5-60-65 - Fuel Conditioning Module PS5-60-UZ-8900E (UCP) | PS5-60-65
PS5-60-66 - Fuel Conditioning Module PS5-60-UZ-8900F | PS5-60-66
PS5-60-67 - Fuel Conditioning Module PS5-60-UZ-8900F (UCP) | PS5-60-67
PS5-60-68 - Fuel Conditioning Module PS5-60-UZ-8900G | PS5-60-68
PS5-60-69 - Fuel Conditioning Module PS5-60-UZ-8900G (UCP) | PS5-60-69
PS5-60-70 - Engine A Cooling system | PS5-60-70
PS5-60-71 - Engine B Cooling system | PS5-60-71
PS5-60-72 - Engine C Cooling system | PS5-60-72
PS5-60-73 - Engine D Cooling system | PS5-60-73
PS5-60-74 - Engine E Cooling system | PS5-60-74
PS5-60-75 - Engine F Cooling system | PS5-60-75
PS5-60-76 - Engine G Cooling system | PS5-60-76
PS5-61-01 - 33kV Switchboard EITS Building (PS5-61-IJ-0001) | PS5-61-01
PS5-61-02 - 6.6kV Switchboard and Transformer LLHT North - EITS Building (PS5-61-IJ-0010) | PS5-61-02
PS5-61-03 - 6.6kV Switchboard and Transformer LLHT South - EITS Building (PS5-61-IJ-0011) | PS5-61-03
PS5-61-04 - 0.4kV Switchboard Office & Facilities Building (PS5-61-IK-0005) | PS5-61-04
PS5-61-05 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0003) | PS5-61-05
PS5-61-06 - 0.4kV Switchboard Power Generator Building (PS5-61-IK-0006) | PS5-61-06
PS5-61-07 - 0.4kV Switchboard EITS Building (PS5-61-IK-0001) | PS5-61-07
PS5-61-08 - Electrical Control System | PS5-61-08
PS5-61-09 - Outdoor Power Distribution Board - PS5-61-IG-0014 | PS5-61-09
PS5-61-10 - Outdoor Valves Distribution Board - PS5-61-IG-0042 | PS5-61-10
PS5-61-11 - Outdoor Valves Distribution Board - PS5-61-IG-0043 | PS5-61-11
PS5-61-12 - EITS 33kV Bld. Normal Auxiliary DP - PS5-61-IG-0008 | PS5-61-12
PS5-61-13 - Power Distribution Board Office Building - PS5-61-IG-0020 | PS5-61-13
PS5-61-14 - Power Distribution Board Workshop & Warehouse - PS5-61-IG-0009 | PS5-61-14
PS5-62-01 - Lighting Control Panel - PS5-62-IE-0001 | PS5-62-01
PS5-62-02 - Lighting Control Panel - PS5-62-IE-0002 | PS5-62-02
PS5-62-03 - Outdoor Emergency Lighting DB - PS5-05-IG-0004 | PS5-62-03
PS5-62-04 - Outdoor Emergency Lighting DB - PS5-05-IG-0006 | PS5-62-04
PS5-62-05 - Guard House Emergency L&SP DB - PS5-05-IG-0007 | PS5-62-05
PS5-62-06 - CRO Generator Building Emergency Lighting DB - PS5-05-IG-0025 | PS5-62-06
PS5-62-07 - CRO Generator Electrical Building Emergency Lighting DB - PS5-05-IG-0026 | PS5-62-07
PS5-62-08 - Outdoor Normal Lighting DB - PS5-61-IG-0006 | PS5-62-08
PS5-62-09 - Outdoor Normal Lighting DB - PS5-61-IG-0007 | PS5-62-09
PS5-62-10 - CRO Generator Building Normal L&SP DB - PS5-61-IG-0015 | PS5-62-10
PS5-62-11 - CRO Generator Electrical Building Normal L&SP DB - PS5-61-IG-0016 | PS5-62-11
PS5-62-12 - EITS 33kV Bld. Emergency L&SP DP - PS5-05-IG-0003 | PS5-62-12
PS5-62-13 - EITS 33kV Bld. Normal L&SP DP - PS5-61-IG-0003 | PS5-62-13
PS5-62-14 - Office Building Emergency L&SP DB - PS5-05-IG-0002 | PS5-62-14
PS5-62-15 - Office Building Normal L&SP DB - PS5-61-IG-0002 | PS5-62-15
PS5-62-16 - Guard Hut A Normal L&SP DB - PS5-61-IG-0111 | PS5-62-16
PS5-62-17 - Guard Hut B Normal L&SP DB - PS5-61-IG-0112 | PS5-62-17
PS5-62-18 - Workshop & Warehouse Normal L&SP DB - PS5-61-IG-0004 | PS5-62-18
PS5-62-19 - Workshop & Warehouse Emergency L&SP DB - PS5-05-IG-0101 | PS5-62-19
PS5-62-20 - Office Building Normal L&SP DB - PS5-61-IG-0010 | PS5-62-20
PS5-63-01 - Electrical Earthing | PS5-63-01
PS5-63-02 - Electrical Earthing - Office and Facilities building | PS5-63-02
PS5-63-03 - Electrical Earthing - Generator Building | PS5-63-03
PS5-63-04 - Electrical Earthing - EITS Building | PS5-63-04
PS5-63-05 - Electrical Earthing - Guard Hut A & B | PS5-63-05
PS5-63-06 - Electrical Earthing - Guard House | PS5-63-06
PS5-63-07 - Electrical Earthing - Workshop & Warehouse | PS5-63-07
PS5-71-01 - CFO Storage Tank Feed Heater | PS5-71-01
PS5-71-02 - CFO Allocation Metering Package | PS5-71-02
PS5-71-03 - CFO Allocation Metering Package (UCP) | PS5-71-03
PS5-71-04 - CFO Storage Tank | PS5-71-04
PS5-71-05 - CFO Transfer Pump A/B | PS5-71-05
PS5-71-06 - Crude Fuel Separation Module | PS5-71-06
PS5-71-07 - Crude Fuel Separation Module (UCP) | PS5-71-07
PS5-71-08 - CFO Pre-Pressure Modules | PS5-71-08
PS5-71-09 - CFO Pre-Pressure Modules (UCP) | PS5-71-09
PS5-71-12 - CFO Service Tank | PS5-71-12
PS5-71-13 - CFO Service Pump A/B | PS5-71-13
PS5-71-14 - Diesel Fuel Transfer and Dispensing Station | PS5-71-14
PS5-71-15 - Diesel Fuel Storage Tank | PS5-71-15
PS5-71-16 - Diesel Fuel Supply Pump A/B | PS5-71-16
PS5-71-17 - Diesel Fuel Distribution Header | PS5-71-17
PS5-71-18 - Diesel Separator Module | PS5-71-18
PS5-71-19 - Diesel Separator Module (UCP) | PS5-71-19
PS5-71-20 - Diesel Fuel Day Tank | PS5-71-20
PS5-71-21 - Diesel Transfer Pump A/B | PS5-71-21
PS5-71-22 - Diesel Fuel Pre Pressure Module | PS5-71-22
PS5-71-23 - Diesel Fuel Pre Pressure Module (UCP) | PS5-71-23
PS5-74-01 - N2 Generation Skid | PS5-74-01
PS5-74-02 - N2 Generation Skid (UCP) | PS5-74-02
PS5-74-03 - Nitrogen Receiver | PS5-74-03
PS5-74-04 - Nitrogen Distribution Header | PS5-74-04
PS5-75-01 - DRA Injection Package | PS5-75-01
PS5-75-02 - Biocide Injection Package | PS5-75-02
PS5-75-03 - Corrosion Inhibitor Injection Package | PS5-75-03
PS5-78-01 - Lifting and handling equipment | PS5-78-01
PS5-79-01 - Electrical Heat Tracing Transformer/Distribution Board 1 (PS5-79-IG-0001) | PS5-79-01
PS5-79-02 - Electrical Heat Tracing Transformer/Distribution Board 2 (PS5-79-IG-0002) | PS5-79-02
PS5-79-03 - Electrical Heat Tracing Transformer/Distribution Board 3 (PS5-79-IG-0003) | PS5-79-03
PS5-79-04 - Electrical Heat Tracing Transformer/Distribution Board 4 (PS5-79-IG-0004) | PS5-79-04
PS5-79-05 - Electrical Heat Tracing Transformer/Distribution Board 5 (PS5-79-IG-0005) | PS5-79-05
PS5-79-06 - Electrical Heat Tracing Transformer/Distribution Board 6 (PS5-79-IG-0006) | PS5-79-06
PS5-79-07 - Electrical Heat Tracing Transformer/Distribution Board 7 (PS5-79-IG-0007) | PS5-79-07
PS5-79-08 - Electrical Heat Tracing Transformer/Distribution Board 8 (PS5-79-IG-0008) | PS5-79-08
PS5-79-09 - Electrical Heat Tracing Transformer/Distribution Board 9 (PS5-79-IG-0009) | PS5-79-09
PS5-79-10 - Electrical Heat Tracing Transformer/Distribution Board 10 (PS5-79-IG-0010) | PS5-79-10
PS5-79-11 - Electrical Heat Tracing Transformer/Distribution Board 11 (PS5-79-IG-0011) | PS5-79-11
PS5-79-12 - Electrical Heat Tracing Transformer/Distribution Board 12 (PS5-79-IG-0012) | PS5-79-12
PS5-82-01 - Sanitary Sewage Collection | PS5-82-01
PS5-82-02 - Sewage Treatment Plant Package | PS5-82-02
PS5-82-03 - Sewage Treatment Plant Package (UCP) | PS5-82-03
PS5-82-04 - Sewage Treatment Plant Discharge Piping | PS5-82-04
PS5-82-05 - Office and Facilities building | PS5-82-05
PS5-82-06 - Guard House Building | PS5-82-06
PS5-82-07 - Guard Huts | PS5-82-07
PS5-83-01 - EITS Building | PS5-83-01
PS5-84-01 - Generator Building | PS5-84-01
PS5-84-02 - Workshop & Warehouse | PS5-84-02
PS5-84-03 - Shelters | PS5-84-03
PS5-86-01 - Shelters | PS5-86-01
PS5-91-01 - Multicore cables & JB | PS5-91-01
PS5-99-01 - Area Completion for Building area | PS5-99-01
PS5-99-02 - Area Completion for Utility area | PS5-99-02
PS5-99-03 - Area Completion for Power Distribution area | PS5-99-03
PS5-99-04 - Area Completion for Process area | PS5-99-04
PS5-99-05 - Area Completion for CFO area | PS5-99-05
PS5-99-06 - Area Completion for Power Generation area | PS5-99-06